## Sheet1
STRENGTHENING, NETWORK & STRATEGIC GRANT: Workplan Template
PROJECT TITLE
Activity |  | Year 1 |  |  |  | Year 2 |  |  |  | Risks (see instructions) |  | Technical assistance to be commissioned
| Person Responsible | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Risks / Assumptions | Risk mitigation
Activity 1: Strengthening the SRHR cluster
Sub-activity 1.1: Mapping of SRHR organisations in target countries | M and E officer/alliance focal networks | [8 empty] | We can reach all organisations working in this area | Use the Alliance mapping tool and ensure it is widely understood and disseminated | bar: Q1 to Q2
Sub-activity 1.2: Identifying youth champions for SRHR at national and local level | Country managers/Alliance focal networks | [8 empty] | There are organised structures in local government for youth participation (not all countries have junior councils) | Work through GL Country managers to indentify country-specific structures. | bar: Q1 to Q2
Sub-activity 1.3: Mapping of LGBTI groups | M and E officer/alliance focal networks | [8 empty] | These groups will want to work with mainstream WR organisations | Pre consultative meetings with regional and national LGBTI groups. | bar: Q1 to Q2
Sub-activity 1.4: Convene SRHR national cluster meetings | Country managers/Alliance focal networks | [8 empty] | There is sufficient traction in each country. | Throrough mapping and development of country-specific strategies. | bar: Q3; Q3
Sub-activity 1.5: Convene a SRHR regional cluster meetings | Alliance manager/Head of Programmes | [8 empty] | National focal networks form a strong base for the regional network | Build strong national networks; ensure regular communication | bar: Q4; Q4
Sub-activity 1.6: Hold discussions forums on SRHR on the Alliance and Governance Community of Practice | Advocacy officer | [8 empty] | Access to Internet, and effective virtual communication | Build in "Making IT work for gender justice" at all Alliance meetings. | bar: Q1 to Q4
Activity 2: Influencing SRHR policies
Sub-activity 2.1: Develop a SRHR model policy and present it to policy makers | Alliance focal networks/country managers | [8 empty] | There is an accepted model that all countries agree to | Develop checklists and build on the guidelines already adopted by SADC. | SRHR expert | bar: Q3; Q2
Sub-activity 2.2: Collect and analyse SRHR data and case studies in target countries based on the SADC Gender Protocol and other SRHR frameworks | Senior researcher/M and E officer | [8 empty] | Up to date and standardised data is available. | Select indicators carefully, using the existing indicators in the Barometer as a base. | bar: Q2; Q2
Sub-activity 2.3: Analyse SRHR national policies and SRHR case studies | Senior researcher/ M and E officer | bar: Q2; Q2
Sub-activity 2.4: Compile, edit, print and launch the SRHR research publication | Senior researcher/ Alliance manager | bar: Q2 to Q3; Q2 to Q3
Sub-activity 2.5: Hold SRHR policy consultations at national level based on the SRHR research findings | Alliance focal networks/country managers | [8 empty] | Governments will be willing to engage with civil society partners | Work closely with SADC sctrutures, and Alliance SRHR lead, SAFAIDS. | bar: Q3; Q2
Sub-activity 2.6: Develop and distribute IEC materials for SRHR (pamphletes, banners and t-shirts) | Advocacy officer/Alliance manager/country managers | bar: Q3; Q2
Sub-activity 2.7: Hold SRHR side events at international, regional and continental platforms | CEO/Alliance Manager/Alliance focal networks | bar: Q1 to Q2; Q1 to Q2
Activity 3. SRHR Campaigns and advocacy strategy
Sub-activity 3.1: Identify digital and social media platforms for SRHR campaigns | Advocacy officer/media coordinator | [8 empty] | Cultural and political sensitivities to SRHR matters. | Have some generic global and regional messaging, eg #SheDecidesSouthernAfrica campign, but allow for country-specific messaging. | Communications expert | bar: Q1
Sub-activity 3.2: Define key messages on SRHR to inform the SRHR campaign and advocacy strategy (these include key messages on SRHR policies, teenage pregnancy, access to SRHR services, GBV, sexual minorities and abortion) | Advocacy officer/media coordinator | bar: Q1
Sub-activity 3.3: Develop and customise the SRHR advocacy strategy for each target country | Alliance manager /focal networks | bar: Q1 to Q2; Q1 to Q2
Sub-activity 3.4: Design and communicate the SRHR advocacy strategy | Advocacy officer/Alliance manager | bar: Q2
Sub-activity 3.5: Hold discussion forums on SRHR on the Community of Practice | Advocacy officer/media coordinator | bar: Q1 to Q4
Sub-activity 3.6:Hold SRHR campaigns on social media and web-based platforms | Junior councillors/young women's alliance | bar: Q1 to Q4
Sub-activity 3.7: Write blogs and press releases on SRHR | Advocacy officer/media coordinator | bar: Q1 to Q4
Activity 4. Enhancing youth involvement on SRHR at a community level
Sub-activity 4.1: Design a local government SRHR module which includes sexuality and SRHR policies | Head of Programmes | [8 empty] | COE for Gender in Local Government will be keen to revisit their gender action plans and strengthen the SRHR component. | Conduct pre consultations with COE Gender Focal Persons. | bar: Q1
Sub-activity 4.2: Develop youth and gender aware SRHR policies for local government | Country managers and facilitators | [8 empty] | Youth will be meaningfully involved in the development of SRHR policies | Share the concept of junior councils where these do not exist; find other structural ways of ensuring youth involvement.
Sub-activity 4.3: Develop/review local government action plans including SRHR and youth | Country managers and facilitators
Sub-activity 4.4:Hold local government training workshops on SRHR in service delivery including junior councillors in 425 local government COEs | Country managers and facilitators | bar: Q2
Activity 5: Promote Youth Involvement in SRHR through IT use
Sub-activity 5.1: Hold podcasts on particular SRHR topic | Alliance manager | [8 empty] | Progressive messages are accepted and do not create tension between youth and their communities. | Be inclusive in the development of messages. | bar: Q2
Sub-activity 5.2: Hold talkshows on particular SRHR topics | Alliance manager /SAFAIDS | bar: Q2; Q2
Sub-activity 5.3: Conduct local community dramas on SRHR and upload the drama videos on website, social media and mobile technology | Country officers /YWA/Junior councillors | bar: Q2 to Q3; Q2 to Q3
Sub-activity 5.4: Hold youth focussed campaigns on social media | Country officers /YWA/Junior councillors | bar: Q1 to Q4
Activity 6: LEARNING, MONITORING & EVALUATION
Sub-activity 6.1: Develop a SRHR summit concept | Alliance Manager | [8 empty] | Sufficient case studies with meaningful impact will be gathered and reported on during the relatively short time span of the project. | Ensure that the annual summits are mentioned at all meetings and become an inspirational pinnacle for the work on the ground. | bar: Q2; Q2
Sub-activity 6.2: Gather SRHR case studies from local government | Country officers | bar: Q2 to Q3; Q2 to Q3
Sub-activity 6.3: Launch call for participation at the SRHR summit | Alliance manager/Governance manager | bar: Q2; Q2
Sub-activity 6.4: Organise and hold SRHR summits in target countries | Alliance focal networks/country managers | bar: Q3; Q3
Sub-activity 6.5: Write summit report outlining best practices | Country managers and facilitators/ Alliance focal networks | bar: Q3; Q3
Sub-activity 6.6: Engage AmplifyChange grantees on SRHR strategies | Alliance manager/country managers and facilitators | bar: Q4; Q4
Sub-activity 6.7: Administer the SRHR local government score card and attitudes survey | Country officers/alliance focal networks | bar: Q2 to Q3; Q2 to Q3
Sub-activity 6.8:Analyse the SRHR local government score card and attitudes survey | M and E officer | bar: Q3; Q3
Activity 8: ORGANISATIONAL SRENGHTENING / CAPACITY BUILDING / SUSTAINABILITY
Sub-activity 8.1: Prepare a fundraising toolkit for SRHR | Alliance manager/Head of Programmes | [8 empty] | SRHR seizes to be funding priority for donors. | Step up advocacy for funding for Women's Rights & SRHR work in regional, continental and global circles. | bar: Q4; Q4
Sub-activity 8.2: Community of Practice discussion forums on SRHR | Advocacy officer/governance officer | bar: Q1 to Q4
Sub-activity 8.3: Identifying of key chapions SRHR at a national level (e.g. government ministers and celebrities) | Alliance manager/country managers and facilitators/alliance focal networks | bar: Q3; Q3
Sub-activity 8.4: Hold interviews with SRHR champions and share these with potential funding partners. | bar: Q3 to Q4; Q3 to Q4