365 Days of Action to End Gender Violence:

From a Campaign to an Action Plan

MADAGASCAR
16 - 18 June 2008

[image: image1.jpg]e
Sela
293







[image: image2.jpg]IF‘E“{" | F‘M_:. g“"‘\ﬂl
i i i 1

Gender and Media Southern Ahlcu




EXECUTIVE SUMMARY
Synopsis
The Madagascar National Action Plan to End Gender Violence is a comprehensive multi sector plan to end gender violence crafted by representatives of government and civil society using the SADC Addendum to the Declaration on Gender and Development on the Eradication of Violence Against Women and Children as a framework. It provides specific targets, timeframes, outputs and budget over a three year period and allocates responsibilities for achieving this. A workshop was held from 16 – 18 June 2008 to develop the National Action Plan which will be canvassed in further consultations
Aim 
The aim of the workshop was to deepen the Sixteen Days of Activism campaigns through developing a set of concrete actions to address gender violence throughout the year, such that the Sixteen Days becomes a time to take stock of progress and set new benchmarks, rather than to simply draw attention to the problem.  

The Sixteen Days of Activism Campaign has gained momentum in countries across Southern Africa and has served to raise awareness amongst ordinary citizens and governments about the high levels of gender violence in the region. However, critics are increasingly questioning its effectiveness.
The Madagascar workshop was conducted in partnership with the Federation for Promotion of Women and Children.

The framework to be used was based on the measures outlined in the SADC Addendum on the Eradication of Violence Against Women and Children to which all Southern African countries are signatory. It is also significant that the Addendum forms the framework around which provisions on gender violence are based in the draft SADC Gender and Development Protocol. The draft Protocol now its final stages will go before the SADC Heads of State at the August 2008 summit for approval.   Key focus areas in the Addendum and draft Protocol include: 

· Legal

· Social, economic, cultural and political 

· Services,

· Education, training and awareness building

· Integrated approaches

· Budgetary allocations 

Targets
The workshop aimed at:
· Non-governmental organisations working in the gender violence sector, especially those who have mounted campaigns during the 16 Days of Activism Campaign. 
· Government, especially departments directly responsible for the delivery of services to survivors of gender violence.

· Policy-makers and researchers. 

· Parliamentarians.

· UN agencies and donors.

· Private sector.

Steps

The main steps: 

· Develop a draft national action plan and checklist for change

· Establish a multi-sector task force to take the plan forward, such that the Sixteen Days becomes a period to benchmark progress, identify new targets, refine the action plan and renew commitments. 
OPENING

Loga Virahsawmy talked about the context of the workshop and the outcome. She talked about the Mauritian experience on how the Gender Action Plan was harmonised with that of the Ministry of Women and launched during the 16 days campaign. Since the UNDP has set a Gender Thematic Group comprising of several partners for the implementation.
The workshop was officially opened by the Senator Johanita Ndahinananjara, who highlighted that Madagascar forms part of countries that have ratified all international conventions to protect women and children and that it is high time to turn the 16 days campaign against gender violence to 365 days, the more so that gender violence concerns Madagascar as well. “Only a multisectorial approach will help to eliminate gender violence”, everybody must react, the executive as well as the population at large. She said that she will encourage all programmes and actions that plan to end gender violence. We will show that Madagascar respects engagements taken and makes sure that all women and girl child have a better future.”

 Legal
Yolande Via Celine, Attorney at Law, gave an overview of gender in the Malagasy laws. She highlighted the articles in the Penal Code that protect women and young girls against rape, sexual violence, attempt against decency, wounds and blows as well as sexual harassment. “The laws exist but there may be problems on its application.” She insisted that there must be laws on domestic violence.

Social, economic, cultural and political 
The Senator Ndahinananjara highlighted that it is only a multisectorial approach that can help to eliminate gender violence. Education has a fundamental role to play against gender discrimination. She, therefore, insisted on friendly schools for girls, revisit programmes and sensitise and attract teachers, food distribution,  and try to keep girls in school as long as possible. “This will prevent girls to contract early marriages which are another obstacle to their education. Without social support, parents cannot send their girls to schools ». She also believes that parliamentarians must talk about gender equality and start by creating a parliamentary committee that will also look at national budgets to include gender issues.

Parliamentarians must be aware of all conventions that protect women and children and must make sure that these conventions are implemented. The media has a role to play in discouraging traditional practices which penalise young girls. Media practitioners must be trained. 
Education, training and awareness building

Mme Mamialisoa, Social Anthropologist made a presentation of the educational system in Madagascar. She gave some statistics on the Malagasy education and highlighted on concrete actions that can help to eliminate gender violence. 
Services

The Commissioner of Police, Romuald Victory and his Assistant confirmed that there are many cases of violence against women in Tamatave. It is the criminal division that is in charge of these cases. In many cases the perpetrators are husbands under the influence of alcohol or rivals. Survivors make complaint directly to the criminal division and sometimes the prosecutor gives directives to open an enquiry. The police sometimes take action even on anonymous cases. They both highlighted that there more cases of rape against minor than adults. The figures are quite high: in 2007, 95 cases of violence were registered and during the six months of 2008 there were 39 cases. “Very often drugs and alcohol are the main problems.”

Christine, former President of an association on gender violence which was created by the Ministry of Population with the collaboration of other partners including the seven churches of Tamatave explained the objective of her organisation. The organisation is mainly to sensitise women and make them more aware of their rights and to give them support.
In 2007, 107 of the 301 cases of gender violence reported to the organisation were cases of domestic violence of which 80 concerned children. The association which also offers counselling does reconciliation before these cases go to court. They too believe that alcohol and adultery are the most important factors that promote gender violence. 
Integrated Approaches and budgetary allocations

Ialfine Tracoulat highlighted that a database on gender violence is of utmost importance to measure gender violence. She also talked about the importance of involving different partners.
The Deputy Mayor of Tamatave suggested that the authorities and NGOs dealing with gender violence should seize national events to advocate and campaign on gender violence. “At the moment football matches of Euro are on, this could have been an opportunity to sensitise members of the public. » 
Gabriel Djankou, Deputy Regional Director of the International Labour Office talked on the different types of sexual harassment at work and against domestic workers.

Two survivors talked about their traumatic experiences. The first one a lawyer, mother of two daughters, went through domestic violence on a permanent basis. Her husband had a mistress and was constantly beating her. He even had a child with the lady. She stayed with him because of her children. She is now refusing to divorce him to prevent him from having a peaceful life with his mistress.

The second woman is the mother of a 14 year old girl who was abused by her step-father. To keep her daughter away from her partner, she sent the girl to her mother who in turn sent her to a restaurant manager. She finished work late and was abused by staff of the restaurant. She lodged a complaint against the rapists but not against the restaurant manager. Now her partner is not happy that the girl is back home.
Closing Ceremony

The Senator Ndahinananjara re-iterated his commitment in the Gender Action Plan developed by participants. Gabriel Djankou, Deputy Regional Director of the International Labour Office, on the other hand promised to support the plan and to finance a study by FPFE. 
Loga talked about the Mauritian experience and advised how the Action Plan can be taken foward with different partners and be implemented.

Nathalie one of the participants who had an appointment with high officials in Tananarive promised to discuss the Action Plan with and seek their collaboration and support for its implementation. 

Annex A – Press Release
Representatives of different associations of Madagascar join hand to end gender violence 

18 juin 2008.  Representatives of Senate, the State Law Office, civil society met during a workshop to work together to end gender violence in Madagascar.

The workshop was organised by Gender Links, a regional NGO, in collaboration with the  Fédération pour la Promotion Féminine et Enfantine. During the three days, participants developed a draft Gender Action Plan to eliminate gender violence. A steering Committee comprising of different organisations represented at the workshop has been set up to make sure of the implementation and follow up actions of the Action Plan.

The Senator Johanita Ndahimananjara, who opened the workshop said « it is only with a a multisectoral approach that gender violence will be eliminated. Education plays a fundamental role against gender discrimination. Education programmes must be revisited at all levels, teachers must be sensitised and girls must be able to stay in schools as long as possible. This will prevent early marriages and other factors that prevent girls to have a better education. »  She highlighted that parliamentarians as representatives of the people must be aware of the clauses on the Convention on Children. “They must see to it that international engagements are respected and implemented.”

Gabriel Djankou, Deputy Regional Director of ILO reiterated his commitment to support the Action Plan.  
Participants agreed to extend the 16 days campaign to 365 days. They highlighted the importance of specific laws to prevent domestic violence, and special clauses on sexual harassment and other sexual offences. They would also like to see rehabilitation and residential centres for survivors with psychological and social aids.  With regards to the HIV and AIDS pandemy participants would like to see centres that offer PEP to all survivors of sexual abuse to minimise the risk of contracting the virus. An important part of the Action Plan concern the sensitisation of the community at large and the training of journalists.   

A Steering Committee comprising of  representatives of Ministries concerned, representatives of NGOs, the media, Madagascar Action Plan and parliamentarians was set up to present the Draft Action Plan to decision makers. But the Senator  Johanita Ndahimananjara, took the commitment of involving her colleagues in the  action plan.

The Plan will be officially launched during the 16 days campaign against gender violence on 25th November 2008. It will be disseminated during the campaign through a variety of activities including radio programmes. Radio programmes will include laws and legislation, services to survivors of gender violence as well as getting survivors to talk.  Representatives of NGOs of Tamatave and Tananarive who participated in the workshop could share experiences during cyber-dialogues, video conferences that will take place during the 16 days campaign.  

The Steering Committee will ensure that recommendations taken at the workshop will be implemented according to deadlines and make regular reports on progress and challenges. 
For futher information, contact,  Ialfine Tracoulat on telephone number :  0320477118

(Workshop participants : the senator, two deputy mayors of Tamatave, the commissioner of police and his assistant, the Deputy Regional Director of the ILO, the Director of the Gender Office of  Tananarive, a member of the State Law Office, Association Todika Tamatave, Association Miara Mizotra, Network of the protection of children against all forms of violence, representation MAP under the office of the President of the Republic, Association Vehivavy Vonona, Association of the Elderly of  Atsinanana, Organisation PRICE, Assoication Mifohaza, Firaisana Tanambao V and members of FPFE)
Annex B: Checklist for change

LEGAL

Specific laws to protect women and children

· Drafting and approval of domestic violence laws.

· Laws voted

Amendments of Family Law
· Children should be allowed to take the names of their mothers
· Family allowance to be given to women who are heads of families
· Fathers who  do not give subsistance allowances to their children should be punished

· The misintaka – rights of mothers to temporarily abandon the family house to two months should be reduced to one month. 
· Residential centres for women under misintaka 

· Divorce – Alimony to be according to number of years of living together.
· Cohabitation should be legal
· Religious marriages should be recognised
· Certificate of celibacy should be verified with the traditional chief before issue
Law on Domestic Violence
· Drafting and approval of law
Law on Human Trafficking
· Drafting and approval
Law on Sexual Offences
· Drafting and approval including laws on sexual harassment in the work place. l

Alimony
Revise law to increase alimony taking into account all domestic expenses 

Complaints
· Simplify procedures
· Accept verbal complaints and follow up actions. 
Tribunals
· Advocate for law practitioners 

· One stop shop for all family matters
· Appoint a woman in the police judiciary service
· Establishment of a Family Court
Sentencing
· Severe sentencing
Rehabilitation of perpetratrors
· Rehabilitation centre
Coordination in the judiciary system
· Better coordination between the police, judiciary and the state law office and regular meetings which include NGOs. 
Sensitisation, awareness and the media

· In house workshops in media houses
Facilities to survivors
· Setting up of rehabilitation centres and give counselling and treatment to abused women by specialists.  Capacity building and empowerment of survivors so that they be economically independent.  

 SERVICES

One stop shop 

· A national centre to take care of violence against women and children.  

Decentralised Services

· Decentralised services by district, region and localities to support survivors of gender violence and abused children. 
Awareness on information and services available
· Disseminate laws and regulations
· Capacity building of those dealing with gender violence
· Distribution of leaflets and information
· Awareness campaign in villages, regions and localities. 
Prevention of gender violence
· Reinforce  detection sytems of gender violence at village and fokontany  

· Train Chiefs of fokontany, security officers of villages and regligious leaders on the detection and how to give information on gender violence
· Put in place a hot line 

· Create centres to listen to survivors
· Appoint and sustain capacity building of those responsible at the centres and law people 

Friendly services for victims
· Put in place centres to help victims
· Put in place a network in regions and at community level
Treatment and accompaniments
· Reinforce treatment and programmes to help victims
· Make available social phsychologist
· Make available PEP in all health centres 

Voluntary testing and councelling
· Add prevention of  STI AIDS in all messages
Infrastructures and places of safety
· Temporary residential centres for victims
· Social rehabilitation of victims
Capacity Building
· Help victims to identify perpatrators
· Train victims to get acess to finance and start their own businesses
· Ensure social and economic rehabilitation of victims
· Social support and rehabilitation of perpatrators
Security in public places 

· Train security officers in villages, heads of fakontany, police officers 

EDUCATION AND AWARENESS
Sensitisation
· 16 days campaign and sensitisation of the public at large as well as in schoolsm, through the media and at all community levels.
· Puppet shows in primary schools on gender violence
· Theatre in secondary schools 
· Films followed by debates in tertiary education
· Desigining and publication of leaflets
· Advertise publicity materials 

· Programmes for television and radio
· Explanation campaigns in rural areas
· Train teachers to detect abused children
· Sharing of best practices
HIV and AIDS and gender violence 

· Sensitisation campaigns in schools
· Training of journalists for better coverage both quantitative and qualitative
· Diminish the incidence of HIV AIDS by the distribution of free condoms
· Fund raising
Calender to extend the 16 days caamnpaign 

· Candle light memorial and other events to commemorate those who died with HIV and AIDS related diseases. 
· Organise activities to mark the international day of HIV and AIDS as well international women’s day, etc. de la Femme, etc

Publications 

· Brochures and leaflets to be put in public places
The Médias

· Train journalists on the coverage of gender violence and encourage survivors to talk.
· Monitoring the media from a gender violence perspective.
· Help media houses to develop policies on gender and HIV and AIDS
· Formation continue pour les journalistes

Media Training 

· Create a resource centre for journalists 

· Directory of sources
SOCIAL, CULTURAL, ECONOMIC AND POLITICAL
Atteindre la communauté par des campagnes de sensibilisation

· Médiatisation, descente sur le terrain, conférences-débats concernant les stéréotypes
Education au développement personnel

· Visites à domicile, réunions de sensibilisation

Dialogues avec les leaders traditionnels dans la communauté

· Organisation d’évènements multiculturels (en dialectes des régions)

· Dialogue, conférence auprès des leaders traditionnels 
Economique

· Assurer que les survivants de la violence envers le genre aient accès à des financements par le biais de formations

Reinforce of informal sector
· Train women to start their own enterprises 

· Train women to apply for tender – ask the help of local government
Capacity Building
· Train unemployed women
Politics
· Politicians as role model
· Train women to go into politics so that they can influence decisions
· Lobby for quota system
· Translation of all laws in Malagasy 
COORDINATION

Integrated approaches and budget 

Put in a place a Steering Committee
· Steering Committee – All concerned ministries, two representatives of NGO/associations, two representatives of the media, two representatives of MAP, two Parliamentarians
· Audit of gender violence and appropriate action
· Database
· Dissimination of information

· Research at national level
Monitoring and evaluation
· Follow up of the Gender Action Plan on a monthly basis as well evaluation
· Updating the Plan of Action
Annex C: Draft National Action Plan to End Gender Based Violence 
Légal

Objectifs stratégiques
1.    
2.

3.

Actions prioritaires

1.

2.

3.

	Objectif
	Action
	Qui
	Cible
	Délai
	Budget

	
	
	
	
	
	Obtenu
	Recherché

	Législations et politiques

Création de lois spécifiques pour renforcer les lois déjà existantes qui protègent les femmes

	· Sensibilisation

· Elaboration de textes légaux

· Application et suivi des lois votées
	La FPFE

ONG Mifohaza

Le ministère pour la Promotion du Genre

Le ministère de la Justice
	Les femmes et les hommes, en particulier les femmes chefs de famille (célibataires, veuves, filles mères, divorcées)
	Fin 2009
	
	

	Législation
Amender le droit de la famille


	· La femme pourra transmettre son nom de famille à son enfant

· Allocation familiale à être versée à la femme chef de famille

· Le père ne versant pas une allocation de subsistance à son enfant, doit être sanctionné

· Le misintaka – droit de la mère de quitter temporairement le foyer conjugal et le mari dispose de deux mois pour venir récupérer sa femme – réduire ce temps à un mois

· Créer un centre d’accueil pour les femmes en misintaka 

· Divorce – les dommages et intérêts doivent être proportionnels à la durée de la vie commune

· Le concubinage doit être reconnu

· Les mariages religieux doivent être légalement reconnus

· Le certificat de célibat doit être vérifié par le chef de quartier du lieu de résidence du demandeur (concubin ou marié selon la coutume)
	La FPFE

ONG Mifohaza

Le ministère pour la Promotion du Genre

Le ministère de la Justice
	Les femmes et les hommes en général
	Fin 2011
	
	

	Violence domestique
· Loi sur la violence domestique


	Elaboration et promulgation du texte
	Les ministères de la Justice et de la Promotion du Genre
	Les femmes comme les hommes
	2011
	
	

	Trafic humain

· Loi sur le trafic humain
	Idem
	Idem
	Idem
	Idem
	
	

	Délits sexuels

· Loi sur les délits sexuels 
	· Elaboration et promulgation d’une loi sanctionnant le viol entre conjoints 
	Idem
	Idem
	Idem
	
	

	Pension alimentaire
· Réviser la loi existante sur la contribution à charge du ménage et la pension alimentaire

	· Augmenter le montant de la pension qui doit tenir compte de toutes les charges encourues par la femme
	Idem
	Idem
	Idem
	
	

	Facilités conviviales pour victimes


	· Création d’un centre de réinsertion pour donner aux survivants des activités génératrices de revenus
	Les ministères de la Justice et de la Promotion du Genre
	Les femmes en général
	Fin 2011
	
	

	Plaintes
· Simplifier les procédures

	Accepter les plaintes même verbales et y donner suite immédiatement
	Services de la police judiciaire et ministère de la Justice
	Femmes et hommes
	Fin 2008
	
	

	Cours de justice

· Centraliser les affaires de famille pour simplifier les procédures
	Nommer une femme au niveau des services de la police judiciaire

Créer un tribunal spécialisé en affaires de famille
	Ministères de la Justice, de l’Intérieur, de la Défense, pour la Promotion du Genre
	Femmes, hommes et enfants
	Fin 2012
	
	

	Condamnations 
· Alourdir les sanctions
	Condamnations fermes et aggravation des peines
	Ministère de la Justice
	
	Fin 2011
	
	

	Justice fortifiante et réhabilitation des auteurs

Création d’un centre de réinsertion


	Réinsertion sociale pour les auteurs de violence envers le genre
	Ministère de la Justice et de la Promotion du Genre, FPFE, ONG
	
	Fin 2012
	
	

	Coordination au sein du système judiciaire
-Une meilleure coordination entre le système judiciaire et la police

	Plus de concertations régulières
	CSI, ministère de la Justice, ministère de l’Intérieur, ministère de la Défense, ONG et société civile
	
	Fin 2008 
	
	

	
	
	
	
	
	
	


SERVICES

Objectifs stratégiques :

1. promouvoir les droits et la protection de la femme et de l’enfant 
2. réduire la prévalence de violence envers les femmes et les filles 
3. assurer la réinsertion des victimes par le biais de l’accompagnement et l’appui socio économique 
Actions prioritaires

1. mettre en place des agents de mobilisation sociale (recrutement, formation, fonctionnement)
2. renforcer la sécurité quotidienne des femmes en mettant les systèmes de détection et de signalement (centre d’écoute, centre d’accueil)
3. appuyer les processus de la réinsertion des victimes (AGR, accompagnement)
	Objectif
	Action
	Qui
	Cible
	Délai
	Budget

	
	
	
	
	
	Obtenu
	Recherché

	Facilités spécialisées

	Services centralisés 
	Mettre en place une cellule de coordination nationale de lutte contre les violences à l’égard des femmes et les enfants 

	Min san 
	Réseaux de protection existants
	Fin 2008
	Infrastructure et mobilier


	Appuis en matériels informatiques et téléphoniques 

	Services décentralisés
	Mettre en place et renforcer une cellule de coordination décentralisée (région, district, commune) de lutte contre les violences à l’égard des femmes et les enfants
	Comité décentralisé + Décideurs 
	Réseaux de protection existants au niveau décentralisé
	1er semestre  2009
	Infrastructure et mobilier


	Appuis en matériels informatiques et téléphoniques

	
	
	
	
	
	
	

	Cours de justice pour délits sexuels
	Plaidoyer auprès des autorités compétentes 

	Réseaux, Mi san,
	Décideurs (min jus, parlement,)
	Avant session parlementaire
	
	Frais d’atelier de plaidoyer 

	
	Mettre en place une cour de justice spécifique 
	MIN SANTE
	PARLEMENT 

MIN JUS
	Session parlementaire 2009
	0
	Budget

	
	Se réunir avec le comité de reforme des lois
	Min santé
	Comité de reforme
	Avant session parlementaire
	
	

	Avis légaux :

Loi sur les violences physiques, morales, psychologiques
	Adopter des lois spécifiques régissant les types de violences conjugales

	Min san, comité de reforme des lois (Min jus)


	Parlement 
	Avant session 2009
	
	

	Programmes contre le viol et les délits sexuels

	Promotion des droits et information sur les services disponibles 
	Vulgariser les lois et textes réglementaires
	Min jus 

Min san 

Réseaux
	Femmes, hommes, enfants 

Décideurs

Leaders d’opinion 
	Fin 2010
	
	Conception et duplication des supports de communication 

Mobilisateur sociaux

	
	Renforcer les capacités des acteurs (mobilisateurs sociaux, agents de santé communautaires)
	Min san 

Réseaux
	Acteurs à former 
	1er semestre  2009
	Salle de formation
	Frais de formation (formateur, participants, logistiques autre que la salle, didactiques)

	
	Doter des kits pour les acteurs 
	Min san, réseaux  
	Acteurs
	1er semestre 2009
	
	Achat des kits par les partenaires 



	
	Organiser des séances de sensibilisation dans les villages, quartiers, 
	Réseaux, acteurs
	Citoyens (femmes, hommes, etc…)
	Fin 2010
	
	Frais de déplacement 

	Réduire progressivement chaque année le taux de violence envers le genre

Protection des droits / Genres

	Renforcer les systèmes de détection des cas de violences envers le genre au niveau des villages, fkt

(système de détection)
	Former les chefs fkt, les agents de sécurité villageois, chefs coutumiers sur la technique de détection et de signalement 
	Min sécurité

Min san, 

Réseaux


	Chefs fkt, agents de sécurités villageois, chefs coutumiers
	1er semestre 2009
	
	Frais de formation 

	
	Mettre en place une ligne verte téléphonique 
	Min san, min jus, min sec
	Orange, celtel, telma
	1er semestre 2009
	
	Coût à évaluer / partenariat 

	
	Doter des appareils téléphones aux centres d’écoute existant et les mobilisateurs 
	Réseaux avec les ministères publics
	
	
	
	

	
	Recruter et renforcer la capacité des personnes responsables des centres d’écoute et de counsulling (para juriste)
	Réseaux 

Min san , min jus
	Parajuriste
	Fin Dec 08
	
	

	
	Ouvrir et faire fonctionner  les centres d’écoute et de counselling
	Réseaux 

Min san 

Min jus
	
	
	
	

	Services conviviaux pour les victimes 
	Mettre en place des centres d’accueil d’urgence pour les victimes de violence 
	Réseaux 

Min san 

Min jus
	
	Fin 2008
	
	Matériels ; monitrices, travailleurs sociaux 

	Traitement complet et soins

	Renforcer les traitements et les programmes de soutien et les services aux survivants de violence envers le genre
	Identifier et mettre en place des personnes spécialistes en accompagnement psychosocial des victimes (centres, à domicile)
	Réseaux 

Min san 

Min jus
	
	
	
	Moyen de déplacement 

Motivation numéraire

	Test de dépistage volontaire et counselling
	Insérer le volet prévention IST SIDA dans les messages à diffuser
	Réseaux 

Min san 

Min jus
	
	
	
	

	
	
	
	
	
	
	

	
	
	
	
	
	
	

	Infrastructures et lieux sûrs
	
	
	
	
	
	

	Lieux sûrs
	Mise en place des centres d’écoutes, centres d’accueil d‘urgence 

	Idem 
	
	
	
	

	Logements secondaires et développement des capacités
	Aider les victimes à identifier leur AGR 
	Accompagnateur, mobilisateurs sociaux
	Adultes Victimes de violence
	Selon le cas 
	
	Soutien financier des victimes 

Frais de suivi 



	
	Former les victimes en gestion et investissement
	Accompagnateur, mobilisateurs sociaux 
	Adultes Victimes de violence
	Durant son traitement
	
	Frais de formation 

	Assurer la réinsertion socio économique des victimes 
	Appuyer les AGR
	Accompagnateur, mobilisateurs sociaux
	Adultes Victimes de violence
	Selon le cas 
	
	Motivation et frais de l’accompagnement 

	
	Suivre les AGR et leur réinsertion 
	
	
	
	
	

	Sécurité dans les lieux publics
	Former les agents de sécurités villageois, les chefs fokontany et les agents de police, gendarmes 

	
	
	
	
	


EDUCATION ET SENSIBILISATION

Objectifs stratégiques

1. Renforcement de la sensibilisation au genre des fournisseurs de services engagés dans                                l’administration de la justice.   
2. Amélioration de la concertation des services entre les unités concernées. 
3. Coordination des échanges de meilleures pratiques à tous les niveaux
Actions prioritaires

1. Sensibilisation au genre (médias et descente sur terrain)

2. Création supports médiatiques

3. Formation des enseignants.

	Objectif
	Action
	Qui
	Cible
	Délai
	Budget

	
	
	
	
	
	Obtenu/

COUT
	Recherché/partenaires

	Education et sensibilisation

	Campagne des 16 jours d’activités et sensibilisation générale
1-Sensibilisation dans les écoles

2-Sensibilisation médiatique

3-Sensibilisation au niveau de la communauté
	1-marionnette dans les écoles primaires
  -théatre dans les écoles secondaires

  - film suivi de conférence-débat dans les lycées et université

-Elaboration de brochures

2-diffusion de spots

  -réalisation des productions

  -insertion du thème dans chaque édition 

3-descente sur terrain en milieu rurale
	1-FPFE

2-FPFE et les journalistes

3-le réseau
	1-Les élèves

2-la communauté

3-population rurale
	1- Une semaine

2-16 jours

3-deux jours         
	
	gouvernement

-ONG PRICE

-UNICEF

-PNUD

	Dans les écoles
Renforcement de l’intégration du thème dans le programme scolaire
	Formation des enseignants

	FPFE en partenariat avec le MENRS
	Les élèves et les étudiants
	Deux jours
	
	Le gouvernement

	Culture, tradition et le rôle des hommes
Changement de mentalité et de comportement
	Sensibilisation au genre 

(médias et descente sur terrain)

Vulgarisation des meilleures pratiques

	FPFE

Autorités locales
	Les hommes

et les femmes
	365 jours
	
	Le gouvernement

ONG PRICE

BIT

	VIH/SIDA et les victimes de violence envers le genre :

-Dimunition du taux de prévalence  -Réduction du nombre des victimes
	Information et sensibilisation
	FPFE  CNLS/MIN SANTE
	COMMUNAUTE
	365 jours
	
	ONU SIDA MINSANTE CNLS

	Utiliser les jours spéciaux sur le calendrier pour étendre la campagne :

-Intégration au  programme.
	Informer 

Vulgariser le thème
	FPFE 

RESEAU
	ASSISTANCES 
	JOURS SPECIAUX
	
	ONG 

GOUVERNEMENT



	Campagnes spéciales :

Plus de conscientisation
	Organiser diverses activités pour faire passer le méssage :spéctacles,concours,théatres ,conférence-débat,concours radiophonique …

Elaboration de supports.

	FPFE 

RESEAU
	COMMUNAUTE
	CAMPAGNES SPECIALES
	
	AUTORITES LOCALES

ONGS

	Publications :

Inf Organisation de soirée commémorative en hommage des victimes du Sida

ormation du public
	Création supports médiatiques

Multiplication supports

Dispatcher

	FPFE


	PUBLIC
	365 JOURS
	
	AGENCE DE COMMUNICATON

	Les Médias
	

	Formation aux journalistes sur la couverture à accorder à la violence envers le genre :

Conviction et initiative des journalistes


	Organiser de séance :information,sensibilisation,conférence-débat 

Formation aux journalistes
	FPFE/Organes de presses
	Les Journalistes
	12 jours
	
	GEMSA/Media Houses

	Monitorage des médias sur la couverture accordée à la violence envers le genre :

Canalisation du thème

 
	Sélection du média

Analyse du contenu

Edition

Publication

Reproduction
	FPFE/GEMSA
	Les Journalistes
	15 jours
	
	GEMSA/MEDIA HOUSES

	Introduire des politiques de genre et de VIH/SIDA dans les salles de rédaction :

Changement de comportement


	Formation des journalistes pour qu’ils diversifient les sources 

Rédiger des articles appropriés 

Eviter des vocabulaires blessants

Eviter les articles stéréotypes
	FPFE/GEMSA
	Média Houses
	15 jours
	
	GEMSA/MEDIA HOUSES/ONUSIDA/CNLS

	Education aux médias 

Professionalisation 

Résponsabilisation
	Conscientiser les Journalistes
Sensibiliser
Former

Création d’un centre de ressources médias
	FPFE/GEMSA/MEDIA HOUSES
	Les Journalistes
	10 jours
	
	Gouvernement 

GEMSA

ONG

CNLS



	
	
	
	
	
	
	

	
	
	
	
	
	
	


SOCIAL, CULTUREL, ECONOMIQUE ET POLITIQUE

Objectifs stratégiques

1. Education de tous les citoyens
2. Sensibilisation des leaders politiques
3. Formation des femmes
Actions prioritaires

1. Eduquer par les Medias, conférences débats, concernant les stéréotypes
2. Dialoguer avec les leaders
3. Renforcer les capacités des femmes.
	Objectif
	Action
	Qui
	Cible
	Délai
	Budget

	
	
	
	
	
	Obtenu
	Recherché

	Social

	Atteindre la communauté par des campagnes de sensibilisation 
	Médiatisation, Descente sur terrain, Conférences Débats concernant les stéréotypes

	Médias, Communauté, ONG & associations, Gouvernement, autorités locales, ONG, Communauté
	Toute la population
	2 mois 
	Ministère
	

	Education aux aptitudes pour la vie
	Visite à Domicile, Réunion de sensibilisation

	Animatrice, ONG, Autorités locales, Chefs traditionnels, religieuses.
	Femmes et enfants
	1 mois
	
	X

	Culturel

	Dialogues avec les leaders traditionnels dans la communauté
Diversité culturelle

Compréhension et respect mutuel
	Organisation des évènements multiculturels (dialecte,..)

Dialogue, conférence auprès des leaders traditionnels 

	Ministère de la Cultures

Parlementaires

Médias
	Genre
	2 ans
	Ministère
	X

	Economique

	Assurer que les survivants de la violence envers le genre aient accès à des financements
	Soutien psychosocial

Soutien psychothérapeutique

Formation du genre (AGR)


	Société Civile,

ONG
	Genre
	1 an
	Ministère(s)

Organismes internationaux
	

	Renforcer le secteur informel
Création d’artisanat

Création de centre d’accueil
	Renforcement de capacités

	Société Civile,

ONG
	Femmes et jeunes filles
	
	
	X

	Développement des aptitudes
	Formalisation du secteur

Renforcement des capacités

	Société Civile,

ONG
	Femmes et jeunes filles
	
	
	X

	Politique
	
	
	
	
	
	

	Mettre en avant des politiciens qui donnent l’exemple
	Mise en exergue dans la presse et Médias 
Discours et actions
	Genre, Médias
	Femmes
	A court termes
	
	X

	Augmenter la participation féminine dans toutes les instances de décisions afin qu’elles puissent influencer les politiques 
	Renforcement de capacités des femmes en politique

Convaincre sur le système de quotas, plaidoyer, lobbying

Traduction de toutes les lois qui protègent les femmes en Malagasy 
	Organisations culturelles, internationales, Femmes formatrice , Femmes leaders
	Politiciennes

Femmes

Jeunes filles
	3 à 5 ans
	GEMSA
	FPFE

	
	
	
	
	
	
	

	
	
	
	
	
	
	

	
	
	
	
	
	
	

	
	
	
	
	
	
	

	
	
	
	
	
	
	

	
	
	
	
	
	
	


COORDINATION

Objectifs stratégiques

1. Mise en place d’une équipe performante et efficiente (Coordination Team)
2. Elaborer un répertoire hétéroclite pour pouvoir mesurer les niveaux de violence envers le genre et de fournir des données de base.
3. S’assurer que toutes les mesures préconisées par le présent P.A sont appliquées de manière intégrée par toutes les parties prenantes
Actions prioritaires

1. Réunion de l’Equipe prédéfinie
2. Collecte des données sur les entités que sur les actions (quantitatifs et qualitatifs)
3. Evaluer mensuellement le plan d’action, y compris l’intégration des partenaires recensés.

	Objectif
	Action
	Qui
	Cible
	Délai
	Budget

	
	
	
	
	
	Obtenu
	Recherché

	Approches intégrées et allocations budgétaires

	I) Structure de coordination/partenariats
	
	
	
	
	

	Mise en place d’une équipe de coordination


	Réunion de l’Equipe prédéfinie lors de l’atelier.
	FPFE
	Les Ministères concernés, 2 représentants des ONG / associations, 2 représentants des médias, 2 représentants de la Maison MAP Toamasina, 2 Parlementaires
	Semaine du 7 juillet
	OUI
(A la charge de chaque entité)
	

	Synthétiser les informations existantes de toutes les parties prenantes oeuvrant dans la lutte contre la violence envers le genre


	Recenser les entités existantes et leurs actions oeuvrant pour la lutte contre la violence envers le genre
	Coordination team
	ONG, Associations, Services Publiques/privés
	2 mois
	
	X

	
	Créer une base de données sur ces entités recensées
	Coordination team
	
	1 mois
	
	X

	Elaborer un répertoire hétéroclite pour pouvoir mesurer les niveaux de violence envers le genre et de fournir des données de base 
	Récolter les données (quantitatifs et qualitatifs) sur les violences envers le genre.
	Coordination team
	Entités recensées
	2 mois
	
	X

	
	Organiser un atelier pour distribuer les fichiers informatisés de la base de donnée aux entités recensés et les formés pour  approvisionner leurs bases et notre base centrales.  
	Coordination team
	Entités recensées
	1 jour
	
	X

	II) Monitorage et évaluation
	
	
	
	
	

	S’assurer que toutes les mesures sont appliquées de manière intégrée par toutes les parties prenantes.
	Mettre en place un bureau en permanence
	Coordination team
	
	
	
	X

	
	Evaluer mensuellement le plan d’action, y compris l’intégration des partenaires recensés.
	Coordination team
	- Responsables des thèmes du P.A

- Partenaires
	
	
	X

	
	Réajuster les actions préconisées par le P.A si besoin est.
	Coordination team et Responsable des thèmes du P.A
	Evaluations
	
	
	X


