DRAFT
SWAZILAND 
365 DAY NATIONAL ACTION PLAN 
TO END GENDER VIOLENCE 

[image: image1.jpg]



Swaziland 365 Day National Action Plan workshop
CONTENTS

Executive Summary 

pg 3
Overview
 pg 7
Check List of Action Points
 pg 11
National Action Plan to End Gender Violence 
 pg 16
Task Team 

pg 35
EXECUTIVE SUMMARY 

The Swaziland 365 Day National Action Plan to End Gender Violence is a comprehensive multi sector plan to end gender violence crafted by representatives of government and civil society using the SADC Addendum to the Declaration on Gender and Development on the Eradication of Violence Against Women and Children as a framework. It provides specific targets, timeframes, outputs and budget over a three year period and allocates responsibilities for achieving this. The action plan, which will be launched during the Sixteen Days of Activism in 2007, includes a coordinating structure for ensuring that all sectors of society are mobilized in the fight against gender violence. See Annex A for checklist of action points and Annex B for Draft National Action Plan. 
The Action Plan was framed against the SADC Addendum on the Prevention and Eradication of Violence against Women and Children which outlines five key areas in which measures must be adopted to address violence against women and children. These are:

· Legal

· Social, Economic, Cultural and Political

· Services

· Education, Training and Awareness

· Integrated Approaches and Budgetary Allocation

Way forward
A technical task team comprising representatives from government and civil society was constituted to work on costing of the action plan in order to come up with a comprehensive budget. See Annex C. The task team will convene a donor round table to market the plan and mobilise resources to ensure that identified programmes are implemented. The draft action plan will go through a process of national consultations before being finalised.  A one day stakeholders meeting will be held including sectors that were not represented at the first drafting workshop such as the business sector and canvassed with the rest of Swazi society. The target is to launch the Swaziland 365 Day National Action Plan to End Gender Based Violence during the 2007 16 Days of Activism Campaign. See schedule in table 1 below:
Table 1: Schedule
	Activity 
	Timeframe
	Who

	Budget
	15th July 2007
	Task team

	Circulation of second draft 
	15 – 30th July 2007
	Task team

	One day stakeholder conference 
	Mid-August 2007
	All stakeholders

	Donor briefing 
	September 
	Task team

	Launch of 365 Day Action Plan 
	During 2007 16 days campaign period
	


Key stakeholders identified

· Business sector
· Key government ministries (coordinated by the Gender Unit)

· UN theme group

· Diplomats

· Gender Consortium

· Media and Arts & Culture groups

· People living with disability (FOTWA)

· Civil society

· Church forum

· FBOs

· Traditional leaders

· Legislators 

· Local government/authorities 

· Youth Council

· Academic institutions including students/UNISWA

· Judicial service community/law society

· NERCHA

· Survivors of gender violence 

· Royal Swaziland Police
Summary of Achievements, Challenges, Strategies and Priority Actions

	Achievements 
	Challenges 
	Key strategies
	Priority Actions 

	LEGISLATION AND THE CRIMINAL JUSTICE SYSTEM

	Policy & Legal Framework
· Adoption and commencement of constitution 
· Legislation: Efforts to promulgate a Child Law and Sexual Offences and Domestic Violence legislation.
· Review of related legislation, e.g. the Teaching Services Commission Act and regulations.
	Policy & Legal Framework
· Non-compliance with international instruments and own commitments and policies.

· There is need for greater  political will

· Mechanisms for need for monitoring        and calling government to account.


	1. To enact/amend laws and domesticate international instruments that deal with GBV
2. To ensure access to justice for survivors of GBV
3. To have a criminal justice system that addresses issues of GBV holistically, in line with the Constitution, and international instruments 


	1. Enactment of laws dealing with GBV

2. Establish structures to deal with GBV

3. Capacity building to train service providers involved in handling cases of GBV

	Justice Delivery System

· Establishment of Specialised Police Unit 

· Courts for in-camera evidence, protection of minors

· Community-based initiatives for dealing with GBV (e.g., LL) 

· Increased availability of counseling services
· Greater awareness and legal literacy
	Justice Delivery System
· There is no holistic approach to the criminal justice delivery system

·  Insufficient coordination of “actors” and service providers in addressing GBV 

· Prohibitive cost of “justice”

· Insufficient resources for  responsible structures

· Cases take too long to go to court
	
	

	SERVICES

	· Increased awareness on services available for survivors of GBV.
· Availability of counselling services provided by the state and NGOs albeit limited.
· Community Initiatives e.g Lihlombe Lekukhalela .
· Toll free lines 999 95 and 9665 provided by SWAAGA and Ministry of Education.
· Survivors are assisted with court preparation when they have to go to court.
· Domestic violence and child protection unit within Royal Swaziland Police service.
· There is a child friendly court within the High Court
· One Government safe House for children and privately owned safe houses. 
	· Limited availability of supporting infrastructure – e.g. counseling services, places of safety, income-generating projects.

· Services for survivors of GBV are disintegrated 
· There is only one child friendly court in the country 

· Some doctors do not want to take rape cases.
· Post exposure Prophylaxis (PEP) given at the discretion of medical personnel.
· Not all police stations have victim friendly interview rooms.
· Many incidences of withdrawal of cases from the police by survivors of GBV
	1. To ensure that all survivors of GBV have information on where to access services.

2. To ensure that these include comprehensive treatment and care.

3. To establish one stop centres where survivors of gender violence can access all the services they need under one roof.


	1. Provision of ready access to PEP as well as treatment to prevent STDs and pregnancy. 

2. Establishing at least a one stop shop in each region.

3. Providing one government supported place of safety in each region.



	Education, awareness and training 

	· There are now high levels of GBV awareness in the country

· There Efforts to bring  change in social, cultural and legal systems 

· Training of service providers such as social workers, police, prosecutors and nurses 

· Campaigns such as 16 days of activism, white ribbon launch 

· Development of IEC materials
· Male Involvement: Community dialogues

· In school empowerment and sensitization

· Wide Media coverage on issues of GBV
· Integration of abuse into school curriculum
	· Insufficient political will

· more focus on awareness creation than prevention 

· Transferring of trained DCS officers.

· Limited participation/ exposure of media personnel.

· Non harmonization of training  services resulting in some communities being over serviced 


	1.Educate men, women, boys and girls on Gender Based Violence (GBV).

2. Train key stakeholders (service providers, media, educators, etc) on sensitive handling of GBV.

3. Develop baseline data on (i) Attitudes to GBV to track behavioural change

(ii) Prevalence of GBV to track rate of reporting.  
	1. Conduct a Gender and Opinion Survey on GBV.

2. Conduct Gender Training for media with a focus on GBV.

3. Conduct regional community dialogues.



	Social, Economic, Cultural and Political 

	· Advocacy initiatives aimed at decision makers such as legislators, political leaders
· Sensitisation and training of traditional/community and religious leaders.


	· Gender violence hardly features on the political agenda.
· Dual system governance of traditional and western concepts that sometimes cause tension

· General societal attitude is that gender violence is largely considered a private and family matter.

· Women still much less economically empowered compared to men.
	1. To challenge gender stereotypes in the way that boys and girls are socialised; affirm positive aspects of culture in the fight against gender violence and challenge those aspects of culture that perpetuate gender violence.

2. To make gender violence a high profile political priority at national and local level.

3. To empower survivors of gender violence and women more broadly, as well as ensure that GBV is properly costed and reflected in the national budget. 


	1. Fund for economic empowerment of survivors of GBV; costing of the plan and reflection in the national budget. 

2. Getting GBV on the political agenda in the run up to local and national elections. 

3. Engaging with advertisers and getting them involved in campaigns to end GBV. 



	Integrated Approaches

	· Establishment of Gender Unit in the  Ministry of Home Affairs, UN Gender Thematic Group and Gender Consortium 

· The Gender Consortium, Gender Unit and the UN have established a system of collaborating their efforts in planning and supporting of gender activities. 
· Launch of the GBV campaign in April 2007

· Commemorate important dates for women such as IWD, 16 days, day of the Child etc. 

· GBV Situational Analysis research

	· Lack of proper coordination of all the planned activities.

· No clear cut off line between Coordination and Implementation. All the three Coordination offices are also implementing on the ground.

· Roles and responsibilities-

· (Justification of the above) All donor funding comes with set targets if not used the money has to be returned. This forces Coordinating bodies to actually implement.  
· There is no consistency  in our interventions, once of actvities. 

· Monitoring and evaluation of our activities is very crucial and will allow us to know those sectors which are receiving little attention.

	1. To create an effective coordinating structure for the National Action Plan at National, Provincial and Local level

2. To popularise the National Action Plan 

3. To ensure that GBV is costed and reflected in the national budget 


	1. Establish, consolidate and implement a representative coordinating structure for implementation of the national action plan

2. Finalise the draft action plan and budget

3. Put in place a monitoring and evaluation mechanism for the action plan 


OVERVIEW 
Swaziland has a dual system of governance characterized by the co-existence of both traditional and modern modes of life.  It has a strong cultural identity, which permeates all forms of social, political and economic interaction. This has a strong bearing on the gender relations and consequently GBV.
Background

The 16 Days of Activism Campaign has gained momentum in countries across Southern Africa and has served to raise awareness amongst ordinary citizens and governments about the high levels of gender violence in the region. However, critics are increasingly questioning its effectiveness. In 2006, the UN Secretary General Study on Violence against Women issued world wide, urged all member states to develop multi stakeholder action plans for ending gender violence. 

Gender Violence in Swaziland

A study conducted in 2006, Gender Based Violence Situational Analysis (Doo  Aphane and Phumelele Thwala, June 1996) which analysed the extent of Gender Based Violence (GBV) in Swaziland found that levels of GBV in the Kingdom of just over one million people was “unacceptably high”. This led to the development of a 12-month awareness campaign that seeks to involve men in projecting a shared national vision of a Swaziland free from Gender Based Violence. The campaign was officially launched by the Ministry of Justice and Constitutional Affairs on the 13th April 2007. 
The study which employed participatory methods guided by Human Rights and Social Relations approaches found that GBV incidents are  escalating at an alarming rate and that urgent action needs to be taken at all levels of Swazi society. The study further corroborates what is asserted in international, regional and continental literature, that women and girls are the most vulnerable groups even though men and boys are also victims of GBV. 

There was a strong indication that tradition and culture have an influence on how women and men in Swaziland conceptualise GBV. This is reinforced by the dual legal system comprising Roman Dutch Law and the Swazi Law and Custom. For example, even though female genital mutilation, trafficking of women and girls and forced pregnancy are commonly identified as GBV internationally and locally these were not raised by interviewees.  
Patriarchy and systematic discrimination against females contribute to causes of GBV.  A number of survivors of GBV interviewed referred to sustained incidences of GBV because of the power the perpetrators had over them as well as the powerful structures within the family which interfere in the way couples handle their relationships.

It is also clear from the study that while there are state and non-state interventions these are in need of strengthening.  For example Health Care sector and Royal Swazi police need training in dealing with GBV cases.  It was also observed that there was a lack of strong and emphatic response by the state.  The state treats GBV as a private matter and this contributes to the serious gap in implementing appropriate interventions.
The campaign is a collaboration of the UN Gender Theme Group (UNGTG) and the NGO Gender Consortium, under the auspices of the Coordinating Assembly of Non- Governmental Organizations (CANGO). Conducted under the theme “A Swaziland Free from Gender Based Violence”, the campaign seeks to build and strengthen community level awareness and involvement in the prevention of GBV through a series of community level dialogues in all four regions and a multi-media strategy.

Development of the 365 Days Programme and National Action Plan 

Building on the campaign highlighted above, a workshop was convened to extend the campaign beyond awareness raising by drafting a multi sector 365 Day National Action Plan to End Gender Violence by Swaziland Action Group Against Abuse (SWAGAA), Gender and Media Southern Africa Network – Swaziland (GEMSWA) and Gender Links (GL). The Gender Unit in the Ministry of Home Affairs contributed resources in support of the workshop. 

The workshop also drew on Swaziland findings in the audit of progress made in ending gender violence undertaken by country chapters of the Gender and Media Southern Africa (GEMSA) Network in 2004, and the “IT for advocacy” training that Gender Links (GL) and GEMSA undertook in nine countries in the region in 2005. 
Officially opened by the Principal Secretary, Misheck Shongwe in the Ministry of Home Affairs the workshop was attended by 24 participants. These were representatives from NGOs, CBOs, CANGO,  business, media, UNDP and government departments including; the Gender Unit in the Ministry of Home Affairs, Ministry of Justice, Ministry of Rural Development and Youth Affairs and Swaziland Royal Police. Two survivors of GBV and one counsellor also participated in crafting the action plan. 

Key issues 
Legislation and Criminal Justice System 

The over arching duality of Roman Dutch Law and the Swazi law and custom creates tension especially when it comes to applying the two systems of governance. In the absence of the Sexual Offences and Domestic Violence Bill which is still being debated, Swazi survivors of gender violence continue to rely on antiquated legislation for recourse. For example; Laws governing sexual offences include: Common law; Criminal Procedure and Evidence Act 67 of 1930; Girls and Women’s Protection Act of 1920; Crimes Act 6 of 1889. The main provisions of the laws governing sexual offences include indecent assault, sodomy, abduction (for sexual purposes), defilement, incest and rape.
There are concerns around definitions inherent in these old laws hence the need to revise them.  For example, what is criminally recognised as rape or what does justice mean for a survivor of gender violence. Current laws have inadequacies regarding “new” offences, and emergent forms of GBV such as human trafficking, willful transmission of HIV among others. There is difficulty in prosecutions; for example around evidentiary issues and resultant inadequacy of sanctions against perpetrators and even would be perpetrators. For example, when considering issues of incapacitation, retribution, rehabilitation and deterrence not enough has been done. There are also concerns around inconsistencies in the application of the law as well as law enforcement agents who are often insufficiently equipped in skills and resources to deal with GBV.
Services

Ensuring access to justice poses serious challenges as this is mainly based on criminal justice process. Law enforcement agents are often insufficiently equipped in terms of skills and resources to deal with GBV. There is much emphasis on the court system and legal process yet the law will not work on its own unless there is infrastructure in place to ensure a holistic approach to dealing with victims and survivors of GBV.

Operation of quasi-judicial structures such as the Teaching Service Commission, the unfriendly court system, law and legal process that are intimidating, negative attitudes and continued maltreatment of those experiencing GBV by law enforcers persist. There is also a fragmented approach by all stakeholders in providing services including NGOs, to survivors of gender violence remain a challenge. Therefore there is a need for an integrated approach to providing services where survivors of GBV will get all services under one roof. It is also imperative to provide specialised services such as family courts, shelters for abused women and adequate training of the service providers.
Education, awareness and training

Through education and awareness by state and non-state agencies a high level of awareness on GBV has been created in the country.  This has been achieved through various programmes including campaigns such as the 16 Days of Activism, involvement of men and boys and integration of GBV in the school curriculum. It is argued that results of positive change in behavior and attitudes by society are beginning to become evident.  

However more still needs to be done to move beyond awareness raising and place emphasis on prevention.  There is need to integrate GBV component in training of service providers for example, for the police, nurses and doctors. Monitoring and evaluation mechanisms need to be put in place to measure whether these interventions are making any difference.
Social, Cultural, Political, Economic
The dual monarchy, comprising the King ruling in conjunction with the Queen Mother, plays an important part in the life of the nation. The system of government combines traditional and western concepts. The King rules in consultation with the cabinet, headed by a Prime Minister, and a bicameral parliament with elected representatives. The legal system consists of customary laws and systems operating side by side with common and statutory laws derived from Roman/Dutch law.
Because of the co-existence of both traditional and modern modes of life, Swazi society has a strong cultural identity, which permeates all forms of social, political and economic interaction. This has a strong bearing on the gender relations. There are aspects within culture that perpetuate GBV. However, every culture has room for respecting women and it is those aspects of Swazi culture that provide entry points for promoting dignity. The strategy will involve affirming the positive tenets of culture while challenging any oppressive tendencies.

A number of factors provide a welcoming environment for this discussion. These include the ratification of CEDAW; a Constitution that includes an equality clause; the government’s gender policy; as well as the SADC Declaration on Gender and Development among other instruments. However there is need to garner more political will to ensure GBV is dealth with decisively. 

Integrated approaches
There has been progress in placing gender on the national agenda.  A Gender Unit within the Ministry of Home Affairs has been established though more needs to be done to ensure that it is well resourced to carry out its mandate. Other gender coordinating structures are UN Gender Theme Group and the Gender Consortium.  

These structures have made it possible to coordinate gender programmes in the country.  However there is still more room for better coordination and pulling of resources to ensure more sustained campaigns are carried out as opposed to once of events.

A monitoring and evaluation mechanism needs to be put in place to measure whether the collective efforts are contributing to ending GBV. 

Check List Of Action Points 
Annex A identifies some of the priority areas under the various themes against which progress can be measured. 

National Action Plan to End Gender Violence 
Annex B is the comprehensive multi-sector action plan. 

ANNEX A
Check List of Action Points

Legislation and the Criminal Justice System 

Legislation

· Lobby for review and harmonization of the dual application of the law, that is traditional and Roman Dutch Law. 

· Domesticate international instruments which we have acceded to especially CEDAW.

· Harmonize Swazi Law and Custom with legislative enactments and common law by 2010.

· Enact reform, repeal or review all laws which are discriminatory and gender insensitive.

· Advocate for passing of the Sexual Offenses and Domestic Violence Bill by 2007. 

· Conduct research on human trafficking in Swaziland to inform legislation and policies. 

· Lobby for and the enactment of the Human Trafficking Law. 

· Finalise the process towards formulation of the Child Bill into an Act by end 2007. 

Access to Justice 

· Lobby for state support legal aid.

· Create legal aid clinics. 
· Establish family courts, child and vulnerable friendly courts. 

· Conduct capacity building for service providers (medical practitioners, legal officers, investigators on matters of GBV).
· To conduct intensive campaigns, trainings, dialogues, on legal literacy.  

Criminal Justice System

· Advocate for victim friendly conditions at police stations.
· Working with who do not want to be more responsive in dealing with rape cases especially those who do not have the expertise to do so. Training for court preparation.
· Reducing the time for cases to go to court.

· Reduce cases going to the wrong courts.
· Increasing the rate of conviction.

· Reducing barriers to holding cases in camera.
· Lobby for compulsory court preparation for victims of gender based violence through government legal services. 
· Advocate for clearance of backlog of cases through either hiring more personnel??? (how can civil society influence this process?).
· Lobby for specialised courts as research shows these facilitate increased rate of prosecution. 

· Conduct Victim Empowerment programmes to minimise or even eliminate withdrawal of cases by victims of GBV especially when a perpetrator is a bread winner.

Services

Information and access to services

· Conduct training of service providers in use of sign language.

· Lobby for and ensure sufficient services are available in rural areas.
· Conduct a Mass media campaign on available services. 

Specialised services

· Create regional one stop centres using existing facilities to ensure that services are made available in a holistic manner.
· Establish family courts in all administrative regions. 

· Establish Child friendly rooms at all police stations and counseling sites

· Create Regional child friendly courts.
Rehabilitation

· Rehabilitation of offenders.

· Establish new and consolidate rehabilitation of offenders programmes.
· Provide counseling to perpetrators of GBV.
Comprehensive Treatment and Care

· Lobby for standardized provision of Post Exposure Prophylaxis (PEP) to all rape cases (HIV, pregnancy) by 2008. Provide regiments for preventing pregnancy and STIs as well as provide counselling for survivors.

· Develop programmes for counselling services for service providers

Infrastructure and Places of Safety

· Lobby for setting up of well resourced government supported shelters for abused women and children on an incremental basis (at least one per region).

· Establish system for women to be able to move from shelters affordable homes.
· Set up skills development and self help groups( economic empowerment programmes) in each region.
· Advocate for safety in public spaces, eg bus stations, parks etc

Education, Training and Awareness

Education and Awareness

· Launch of GBV National Action Plan as complimenting the recently launced GBV campaign.
· Design and develop targeted IEC materials on GBV.
Involvement of men

· Engage men and boys on issues of GBV in communities through hosting regional men’s dialogues facilitated by men.

Involvement of survivors

· Document first hand accounts from survivors of GBV.

· Capacity building in public speaking, lobbying and advocacy through integration of survivors in public awareness campaigns.
Stretching the 16 days to 365 

· Hold 16 days of Activism campaign events annually attended by high profile people carrying key messages.
· Mount at least one high profile campaign each year  e.g. Take Back the Night campaign

· To incorporate GBV activism into existing campaigns that stretch across the year, e.g International Women’s Day, Human Rights Day, Child Protection Week, Day of the African Child, National Day, etc.
GBV and HIV and AIDS

· Conduct campaigns on the link between GBV and HIV and AIDS and PEP.
Schools

· Design new and consolidate existing education materials on GBV appropriate for different age groups.

· Integration of education materials into school curriculum appropriate for different levels.

· Train educators/teachers on GBV.
· Promote the idea of safer schools through developing policies for dealing with GBV in schools

Training of service providers 

· Design GBV curriculum for training of service providers by December 2008.

· Finalise designing of the police training module on GBV by December 2007. 

· Roll out of GBV training for service providers from January 2009. 

The Media

· Develop and air radio programme with a focus on GBV.
· Finalise and roll out of a women’s programme which has a focus on GBV from July 2007/  

· Develop a TV soap programme focusing on GBV.
· Host TV talk shows on GBV. 

· Design messages on GBV for advertising in print media, billboards, public spaces, packaging.
· Conduct media monitoring.
· Engage with the media through conducting quarterly meetings with them.
· Development of Gender and HIV and AIDS newsroom policies by 2009.
· Conduct media training workshops on reporting GBV.
· Advocate for rotating of journalists on the GBV beat by media mangers.
· Conduct media literacy training especially among women (consumer activism).
Monitoring and Evaluation

· Establish targets and indicators; conduct regular opinion surveys

· Conduct regular media monitoring & comparative analysis

Social, Cultural, Economic And Political

Social and Cultural

· Mainstream gender in the “youth menu” and in the youth centres. 

· Mainstream gender and its relationship to HIV and AIDS in youth organizations eg Boy Scouts, Girl Guides, Super Buddies (boys and girls under 15) and in their publication (Super Buddies).
· Workshops with lutsango (women); libutho (older men); imbali (young women); tingaaja (young men) separately and together.

· Develop IEC materials; arm bands.  

· Gender training for cultural workers, especially script and song writers. 

· Support these groups in producing popular plays, songs, theatre that challenge stereotypes.
· Competition and awards for popular plays, songs, theatre that challenge gender stereotypes.

· Monitor advertisements and send out alerts.
· Form an association of advertisers and engage on gender stereotypes in advertising.

· Engage advertisers in campaigns against gender violence.
· Award for gender aware advertising as part of media awards.
· Engage the Premier League to brand the white ribbon.
· Include an award for sports personality or association that has proven to be gender aware.

· Gender sensitisation and awareness training with key functionaries, eg counselors.
· Follow up backstopping at regional level.
· Mainstream knowledge of gender violence in counseling training.  

· Monitoring and backstopping.
· Establish a Men for Change organization. 

· Audit of good practice within traditional system with regard to GBV; how traditional courts and systems address GBV

· Hold gender dialogues with traditional authorities. 

· “Peace begins at home” family of the year award.
Political 

· Sensitisation of politicians/ portfolio committees to gender, and gender violence. Take advantage of elections.

· Civic education to ensure that gender violence is put on the agenda especially during the election year. 

· Profile champions of gender violence.  

· Gender sensitization for Councilors soon after elections and zone leaders, central committees. 

· Support to local councils in urban areas and tikundla in rural areas  to develop local action plans for ending gender violence.
· Documenting and sharing good practices of fighting gender violence at local level. 

Economic Empowerment

· Priority for survivors of gender violence in job creation to get out of the dependency syndrome.
· Educate and provide information to survivors on economic opportunities available.
· Advocate for easier access to capital; seed funding for women including survivors of gender violence.
Integrated Approaches and Budgetary Allocations

· Create a coordination structure, ensure regular meetings

· Ensure that partners are recognized to avoid turf wars.
· Ensure that all stakeholders are involved eg medical doctors, Police Domestic Violence and Protection Unit in the National Action Plan. 

· Design and implement a popularisation strategy of the National Action Plan (e.g. by developing comprehensive communication strategy.
· Costing of plan and donor round table.
· Develop tools for conducting regular monitoring and evaluation to gauge progress on implementation of the plan.
ANNEX B

DRAFT

SWAZILAND 365 DAY NATIONAL ACTION PLAN TO END GENDER BASED VIOLENCE
	OBJECTIVE
	ACTION
	WHO

	TARGET 
	TIMEFRAME
	 BUDGET 

	
	
	
	
	
	Secured 
	Sought 

	LEGISLATION AND THE CRIMINAL JUSTICE SYSTEM

	Create an enabling environment in which GBV is addressed using a rights based approach
	Lobby for review and harmonization of the dual application of the law, that is traditional and Roman Dutch Law. 


	Gender Consortium, media practitioners, 

Government ,

Law Reform commission
	Dual application of the litigation reviewed and harmonized  
	2007-2008 
	
	

	
	Harmonize Swazi law and Custom with legislative enactments and Common Law


	AG/ Parliament
	Laws harmonized
	2010
	
	

	
	Domesticate international instruments which we have acceded to especially CEDAW


	Parliament, MOJ, cabinet, Gender Consortium, media practitioners, 

 
	All international legislation domesticated.
	2009
	
	

	
	Conduct an audit of all remaining discriminatory legislation; enact, reform, repeal or all laws which are discriminatory and gender based
	MOJ,

Parliament, Law Reform Commission 
	All discriminatory legislation removed
	2007-2009
	
	

	To pass  comprehensive, specific legislation to address GBV


	Passing of the Sexual Offenses and Domestic Violence Bill 
	Gender Consortium, Parliamentary women’s caucus, Government 
	The  Sexual Offenses Bill enacted 
	December 2007
	
	

	To enact a law that deals with Human Trafficking with emphasis on women and children 


	Conduct research on human trafficking in Swaziland 


	Gender Consortium, Parliamentary women’s caucus, Government
	Data on human trafficking in Swaziland compiled
	2007-2008
	
	

	
	Lobby for and enact the Human Trafficking Law
	MOJ, Parliament/ civil society
	Law passed 
	2008
	
	

	To pass comprehensive legislation to protect children 
	Finalise the process towards formulation of the Child Bill into an Act 
	Gender Consortium, Parliament, MOJ
	Child Act enacted 
	2007-2009
	
	

	To ensure availability and affordability of structures for efficient justice delivery  
	Lobby for state supported legal aid; establishment of legal aid clinics decentralized across the country

 
	Gender Consortium, Government (Min of Justice, Finance ) Parliament 
	Legal Aid clinics, family courts, child and vulnerable friendly courts established. 


	2007-2009
	
	

	Raise awareness on how to access justice 
	To conduct campaigns, trainings, dialogues, on legal literacy  
	Gender Consortium, (Ministry of Justice, Finance) Parliament
	Awareness on Access to justice 
	2007-2008 intensive; ongoing
	
	

	To have a criminal justice system that addresses issues of GBV holistically in line with the Constitution, and international instruments 


	Creating police stations that are friendly to victims (legislation)
	Gender Consortium, Government,  Parliament, stakeholders, civil society
	Enjoy a free gender violence criminal justice system
	2007-2015
	
	

	
	Working with doctors who do not want to take rape cases or do not have the expertise to do so and conduct

training on court procedures
	
	
	
	
	

	
	Reducing the time for cases to go to court; cases going to the wrong courts. 
	
	
	
	
	

	
	Lobby for establishment of family courts
	Civil society
	
	
	
	

	
	Compulsory court prep
	Police; DPP; counselors 
	Increasing the rate of conviction
	
	
	

	To reducing the withdrawal of cases especially when a person is a bread winner.
	Reducing barriers to holding cases in camera
	
	
	
	
	

	Ensure survivors of GBV can sustain themselves to avoid being trapped in abusive relationships
	Economic empowerment
	Gender Unit, Gender Consortium, Min of Finance 
	Survivors of violence become economically independent
	
	
	

	
	To enhance access to juvenile justice
	
	
	
	
	

	SERVICES

	INFORMATION AND ACCESS TO SERVICES

	To ensure that all survivors of gender based violence including people with disability are aware and have access to services
	Training of service providers in use of sign language.
	Civil Society 
	One sign language training for various stakeholders per year : police, nurse, prosecutor, interpreters, counselors, educators 
	2007
	
	

	
	Making services available in rural areas
	UNICEF, NERCHA 
	215 reached; extend to all 360 Community Child Protectors- Lihlombe Lekukhalela  
	2007- 2008
	
	

	
	Mass media campaign on available services 
	Civil society, media 
	Adverts, IEC material 
	Ongoing
	
	

	SPECIALISED SERVICES

	Provide a holistic approach to provision of services to survivors of GBV to overcome the current disintegrated approach to services.
	Create regional one stop centres using existing facilities to ensure that services are available under one roof 


	Min of Health, Min of Justice, RSP, Gender Unit in MHOA, Civil Society   
	At least one stop centre established in each region 
	2011
	
	

	Specialized courts (e.g. family courts)


	Establish family courts in all administrative  regions 
	Ministry of Justice 
	One family court per region 
	2011
	
	

	To provide child friendly interview rooms at all police stations.
	Child friendly rooms at all police stations and counseling sites
	RSP, UNICEF 
	23 victim friendly interview rooms (ie in all police stations) 
	2008
	
	

	To ensure that Child friendly courts are accessible across the country (currently only one in the High Court). 
	Regional child friendly courts
	Ministry of Justice 
	At least one child friendly court per region 
	2011
	
	

	REHABILITATION 

	To prevent re occurrence of GBV through rehabilitation of offenders 
	 Rehabilitation of offenders
	SACRO

Correctional Services 
	Structured sensitisation and counseling of   imprisoned offenders; reintegration and monitoring
	ON GOING 
	
	

	Peace building and reconciliation 
	Provide counseling to perpetrators 
	Civil Society, Pastors 
	Increase in the number of perpetrators seeking counseling services 
	Ongoing 


	
	

	COMPREHENSIVE TREATMENT AND CARE

	Strengthen treatment and support programmes and services for survivors of gender-based violence.


	Provision of Post Exposure Prophylaxis to all rape cases, STD, prevention of  pregnancy as well as counseling.
	Ministry of Health, Civil Society 
	All rape cases receiving PEP and other forms of treatment including counseling.
	2007/2008
	
	

	To provide socio psychosocial support to service providers 
	Counselling services for service providers
	Ministry of Health and Ministry of Public Service
	One psychologist for service providers per region 
	2008
	
	

	INFRASTRUCTURE AND PLACES OF SAFETY

	To provide places of safety for abused  women and children


	Government supported shelter for abused women and children 
	Ministry of Health and civil society  
	One per region 
	2011
	
	

	To ensure that survivors of GBV have access to secondary housing
	Establish system for women to be able to move from shelters into affordable homes.
	Ministry of Housing
	All women taking temporary refuge at places of safety able to move to their own homes.
	Ongoing
	
	

	Ensure safety in public spaces.


	Secure bus stations, parks etc
	Min of Housing and Urban Development
	Adequate lighting; policing; bush clearing; improved market structures; clearing derelict buildings.
	On going 
	
	

	EDUCATION, TRAINING AND AWARENESS

	To raise awareness and enhance understanding of Gender Based Violence (GBV) in communities and place a greater focus on prevention.
	Launch of GBV campaign

Design and develop targeted  IEC materials on GBV
	Gender Unit in MHOA, Gender Consortium, Business partners, NGOs, CBOs, GEMSWA, MISA-Swaziland
	Targeted messages on GBV reaching out to men, women, boys and girls 
	April 2007


	
	

	Create a critical mass of  men and boys involved in ending gender based violence


	Engage men and boys on issues of GBV in communities through hosting regional men’s dialogues facilitated by men; 

Establish an independent network of men starting with NAP workshop
	Gender Unit in MOHA, Gender Consortium, Men’s groups, FBOs, CBOs, Theatre groups, SWAGAA
	Four dialogues held per region with increased men’s participation
	Increased involvement of men in ending GBV 
	315 000
	

	To involve survivors of violence in GBV campaigns
	Document first hand accounts from survivors 
	GEMSWA, SWAGAA, MISA
	Twenty first hands published and distributed through mainstream media and relevant stakeholders.
	July – Dec 2007
	350 000
	

	
	Capacity building in public speaking, lobbying and advocacy through integration of survivors in public awareness campaigns
	GEMSWA, SWAGAA, MISA
	
	
	
	

	To stretch the 16 days campaign to 365 through using this high profile campaign to heighten awareness of GBV 
	Hold 16 days of Activism campaign events annually attended by high profile people carrying key messages, eg Take Back the Night campaign; White Ribbon Launch. 
	Gender Unit in MOHA, Gender Consortium,

GEMSWA etc
	High profile campaign each year.
	25 November-10 December
	
	

	
	To incorporate GBV activism into existing campaigns that stretch across the year e.g International Women’s Day, Human Rights Day, Child Protection Week, Day of the African Child; National Day


	Gender Unit in MOHA, Gender Consortium, GEMSWA etc
	GBV features on all major dates in the calendar.
	Year long
	
	

	Create awareness on the link between GBV and HIV and AIDS


	Campaigns on the link between GBV and HIV and AIDS.
	GEMSWA, (Identify HIV&AIDS organisations)
	One high profile campaign held each year
	Sept – Dec 2007

Ongoing
	210,000
	

	Educate school going boys and girls on GBV 
	Design new and consolidate existing education materials on GBV appropriate for different age groups.
	Min of Educ, Gender Unit in MOHA, SWATCYP.
	Pupils who are educated in Gender Violence.
	August 2007 – March 2009
	
	

	
	Integration of education materials into school curriculum appropriate for different levels.


	Min of Educ, Gender Unit in MOHA, SWATCYP, 
	Pupils who are educated in Gender Violence.
	April 2009 – March 2010
	
	

	
	Train educators/teachers on GBV 
	MOE
	All teachers trained 
	Over the three years
	
	

	
	Policies for dealing with GBV in schools
	MOE
	Comprehensive policy for GBV in schools
	2008
	
	

	Integrate GBV into training of service providers
	Design GBV curriculum for training of service providers.


	SWAAGA, Save the Children, TASC, Gender Unit in MHOA, Min of Health, Min of Justice, service providers
	Standardised curriculum for training service providers for GBV.
	August 2007 – December 2008
	
	

	
	Finalise designing of the police training module on GBV 
	SWAAGA, Save the Children, 
	Standardised curriculum for training police 
	By December 2007
	X
	

	
	Roll out of GBV training for service providers 
	SWAAGA, Save the Children, TASC, Gender Unit in MHOA, Min of Justice, service providers 
	All service providers trained in GBV 
	
	
	

	Effective use of multi-media products to end gender violence 


	Develop and air radio programme with a focus on GBV
	Gender Unit in MOHA, Gender Consortium
	Radio programme focusing of GBV developed and aired - Women, men, boys and girls have increased awareness and better understanding of GBV
	April 2007 – Dec 2007
	X

91,000
	

	
	Finalise and roll out of a women’s programme which has a focus on GBV  
	SBIS 2,

Gender Consortium
	An increase in awareness on GBV and provide platform for engagement by communities
	July 2007 – ongoing 
	
	X

200,000

	
	Develop a TV soap programme focusing on GBV
	Gender Unit in MOHA, Gender Consortium, an identified Swazi TV channel
	TV soap programme focusing of GBV developed and aired – increased public discourse on GBV 
	April 2007 – Dec 2007
	
	X

33,000

	
	Host TV talk shows on GBV 
	Gender Unit in MOHA, Gender Consortium, an identified Swazi TV channel
	Regular Television Talk Shows held and increased public discourse on gender violence 
	September 2007 – ongoing 
	
	

	
	Design messages on GBV for advertising in print media, billboards, public spaces, packaging
	Gender Unit in MOHA, Gender Consortium, NGOs, CBOs, Business sector
	Multi-media messages designed and placed in print media as well as distributed through various channels
	April – Dec 2007
	
	

	To promote balance, fairness, sensitivity and compliance with ethical standards  in media coverage.
	Media monitoring, 

Engaging with media houses

Quarterly meetings with the media to review progress. 


	MISA; GEMSWA
	Direct engagement with all media houses on covering GBV; ongoing engagement. 
	July-Oct 2007
	
	

	
	Development of Gender and HIV and AIDS newsroom policies 
	GL/MISA MAP project;

SNAJ, Swaziland Editors Forum, MISA, GEMSWA, Media houses 
	All media houses have Gender and HIV and AIDS policies by 2009
	2006 - 2009
	Covered 
	Covered 

	To build capacity of  reporters to report on GBV in a balanced and sensitive way.
	Training workshops on covering GBV

Rotating of journalists on the GBV beat
	Media houses, UNISWA (dept of JMC), Business Mgt and Comm. Centre, SIMPA,
	Media that fulfills their role in combating GBV
	Ongoing 
	
	

	Creating media literate consumers who can challenge the media
	Conduct media literacy training especially among women (consumer activism)
	Gender Links, GEMSWA, MISA-Swaziland, 
	
	
	
	

	Media legislation; self regulation 
	
	
	
	
	
	

	To measure whether attitudes are changing so as to target campaigns more effectively
	Establish targets and indicators; conduct regular surveys
	GEMSWA, Gender Consortium 
	An incremental positive shift in attitudes towards GBV 
	Begin January 2008; every five years
	
	

	Assess media performance on reporting GBV.


	Conduct regular media monitoring & comparative analysis
	MISA

GEMSWA
	Before and during every Sixteen Day campaign
	November - December each year
	
	

	SOCIAL, CULTURAL, ECONOMIC AND POLITICAL

	To challenge the way that boys and girls are socialised
	· Mainstream gender in the “youth menu” and in the youth centres 
	Swaziland National Youth Council (Ministry of Regional development)  
	Workshops on gender violence as part of the programmes
	Ongoing 
	
	75 000

	
	· Mainstream gender and its relationship to HIV and AIDS in youth organizations eg Boy Scouts, Girl Guides, Super Buddies (boys and girls under 15) and in their publication (Super Buddies) 
	MRDYA; SNYC; youth organizations 
	Workshops to review curriculum and practice 
	Over the three years 
	
	150 000 

	To initiate dialogues on gender and culture
	· Workshops with lutsango (women); libutho (older men); imbali (young women); tingaja (young men) separately and together.

· IEC materials; arm bands  


	Home Affairs (Sports and Culture division); Ministry of regional development
	Annual incwala at national and regional level; 

Annual marula ceremony 

Events at 55 tinkundla as part of the decentralization process
	Ongoing at strategic events throughout the year. 
	 
	1 500 000

	To challenge gender stereotype in popular media, culture and music
	· Gender training for cultural workers, especially script and song writers 
	SWIT; SWATCYPT; Swaziland Music association; Association of Swaziland Theatre Group; SNCC  
	Major national three day workshop bringing together 50 cultural workers 
	2007 
	
	80 000

	
	· Support these groups in producing popular plays, songs, theatre that challenge stereotypes
	Ministry of Home affairs (Sports and Culture)
	Regular productions
	Ongoing 
	
	7 500 000

	
	· Competition and awards for popular plays, songs, theatre that challenge gender stereotypes.
	Ditto 
	Annual awards that empower and sustain the sector (eg instruments
	Every year. 
	
	1 500 000 

	To engage with advertisers on messaging on gender violence 
	· Monitor advertisements and send out alerts 
	GEMSWA/ GL 
	Report on gender stereotypes in advertising 
	2007/2008
	
	150 000

	
	· Form an association of advertisers and engage on gender stereotypes in advertising.
	GEMSWA advertisers 
	
	2008 
	
	60 000 

	
	· Engage advertisers in campaigns against gender violence
	GEMSWA
	
	Ongoing 
	
	In kind 

	
	· Award for gender aware advertising as part of media awards
	SNAJ
	Annual award
	
	
	150 000 

	To promote the ending of gender violence through sport personalities and activities. 
	· Engage the Premier League to brand the white ribbon
	Ministry of Home Affairs; National sports Council 
	Sixteen Days of Activism 
	Annual 
	
	In kind 

	
	· Include an award for sports personality or association that has proven to be gender aware.
	National Sports Council 
	Annual Sports awards
	Annual 
	
	45 000 

	To engage with faith based organisations on ending gender violence
	· Gender sensitisation and awareness training with key functionaries, eg counselors
	Swaziland Conference of Churches; Swaziland Council of Churches; Swaziland League of Churches; Swaziland Independent League
	National workshop 
	2007 
	
	240 000 

	
	· Follow up backstopping at regional level 
	Ditto 
	Regional workshops 
	Annual 
	
	240 000 

	
	· Mainstream knowledge of  gender violence in counseling training  
	SCOT 
	Peer education workshops with GBV counselors eg SWAGAA. 
	Ongoing 
	
	135 000 

	
	· Monitoring and backstopping
	Gender consortium 
	All church counselors provide effective support on GBV 
	Ongoing 
	
	300 000 

	To engage with traditional structures and institutions on ending gender violence
	· Audit of good practice within traditional courts and systems that handle GBV
	UNISWA, WLSA 
	
	2008 
	
	150 000 

	
	· Gender dialogues with traditional authorities 
	UNISWA, WLSA
	360 chiefdoms 
	Over the three years 
	
	100 000

	
	· “Peace begins at home” family of the year award
	Ministry of Regional Development 

Traditional structures
	Annual award 
	Annual 
	
	

	POLITICAL 
	
	
	
	
	
	

	To involve public officials and royal family to be bearers of messages of condemning GBV in the media and public spaces throughout the year
	· Sensitisation of politicians/ portfolio committees to gender, and gender violence. Take advantage of elections.
	Gender unit; Vote for Women alliance (WLSA, CANGO)  
	Before elections 
	By August  2008  (before elections) and with new politicians
	
	90 000 

	
	· Civic education to ensure that gender violence is put on the agenda especially during the election year. 
	Electoral Office; CANGO Gender Consortium 
	Before elections
	By August 2008 
	
	150 000 

	
	· Profile champions of gender violence through public nominations.  
	
	
	
	
	

	To encourage local communities to develop models and good practice in ending gender violence 
	· Gender sensitization for Councilors soon after elections, zone leaders, central committees  
	AMICAL; Municipal; Ministry of Housing and Urban Development 
	All key local leaders trained  
	Soon after the October 2007 
	
	300 000 

	
	· Support to local councils in urban areas and tikundla in rural areas  to develop local action plans for ending gender violence 
	Ditto 
	All local structures have action plans 
	Over the three years 
	
	600 000 

	
	· Documenting and sharing good practices of fighting gender violence at local level. 
	MISA/GEMSWA 
	Annual meeting 
	Every year after plans in place
	
	400 000

	ECONOMIC EMPOWERMENT

	To ensure economic empowerment of survivors of GBV


	· Priority for survivors of gender violence in job creation to get out of the dependency syndrome
	Ministry of Enterprise and Employment; SME Unit; SWAGAA  
	All survivors of gender violence are economically empowered and skilled 
	Ongoing 
	
	1 500 000 

	To empower women economically as part of a long term strategy to pre-empt gender violence, especially for the most vulnerable women. 
	· Information 

· Access to capital; seed funding 
	Ministry of Enterprise and Employment through SME Unit; handicraft sector; Association of Swaziland Business Community 
	Rural women; women in the informal sector 
	Ongoing 
	Existing 
	Existing 

	INTEGRATED APPROACHES

	COORDINATING STRUCTURE

	To create an effective coordinating structure for the National Action Plan at National, Provincial and Local level


	(Coordination versus implementation)
	
	
	· 
	
	

	
	Ensure that partners are recognized to avoid turf wars
	
	
	· 
	
	

	
	Ensuring that all stakeholders are involved eg medical doctors, Police Domestic Violence and Protection Unit 
	
	
	· 
	
	

	
	Programme as opposed to event based approaches
	
	
	· 
	
	

	To popularise the National Action Plan 


	
	
	
	
	
	

	RESOURCE MOBILISATION

	To ensure that GBV is costed and reflected in the national budget 


	Lobby the Planning and Budgetary Committee  
	Ministry of Finance and Economic Planning; Portfolio Committees  
	Distinct budget line for ending gender violence. 
	March 2008 
	
	30 000

	MONITORING AND EVALUATION

	To put in place a mechanism to measure progress in ending gender violence
	To put in place a monitoring and evaluation framework
	Task team, Gender Unit,
	Measurable indicators put in place
	Ongoing
	
	

	
	
	
	
	
	
	


ANNEX C: TASK TEAM

A task team was constituted to work on a budget for the action plan. See table 2 below:
Table 2: Task team members

	Theme
	Who 

	Legal and Criminal Justice

	Sizakele Hlatshwayo/Mhlanga

	Services


	Nonhlanhla Dlamini – SWAGAA

	Public Awareness
	Ncane Maziya - GEMSWA

	Social Cultural and Economic

 
	Sifiso Ndlangamandla 
Bhekisisa Magongo

	Coordination


	Nonhlanhla Dlamini – Gender Unit (MOHA)

	Budget Expert



	Sakina Morris - UNDP


[image: image2.png]



PAGE  
35

