BEITBRIDGE GENDER ACTION PLAN EXAMPLE – STRENGTHENING SRHR, GRB & INTEGRATION INTO COUNCIL PLAN

Step 1: Replace the section highlighted in green with the updated SRHR plan

Step 2: Compare the plan with the council plan and conduct an audit. Are all the provisions of the gender action plan captured in the council action plan? If not, what steps need to be taken to fully integrate the plan into the Council plan.

Step 3:  Compare the plan with the council budget. Are these provisions budgeted for? Where? If not, how can this be rectified?

- Gender Policy Framework

| BASELINE | SDG | POST 2015 SADC PROTOCOL TARGET | INDICATORS | TARGET GROUP | ACTIONS | OUTPUT | WHO | TIME FRAME | BUDGET | LOCATION IN STRATEGIC PLAN OR IDP |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Gender Policy Framework |  |  |  |  |  |  |  |  |  |  |
| Strategic objective: Increase the local authority’s level of awareness around national, regional, international commitments that the country has made especially the Post 2015 SADC Protocol on Gender and Development, SDG s and the National Gender Policy. |  |  |  |  |  |  |  |  |  |  |
| What is the current level of awareness? 80% | Adopt and strengthen sound policies and enforceable legislation for the promotion of gender equality and the empowerment of all women and girls at all levels | State Parties shall develop and strengthen specific laws, policies and programmes to achieve gender equality and equity. | An active gender draft policy to be approved by the local authority. | Women, girls, men and boys | Gender sensitization meetings 3 Workshops per quarter | -Gender responsive budget -Gender aware women and girls- behaviour change | Administration Engineering Finance department | Dec 2017 | $1000 |  |
|  |  |  | Code of conduct Sexual harassment policy Induction policy | Council department heads, residents , employees Policy Makers | Adoption and implementation of gender sensitive policies and bylaws Trainings Sensitization | Gender responsive council. Gender sensitive budget. Knowledgeable community | Heads of departments Councillors | Dec 2017 | - |  |
| Has a gender policy framework been drafted and approved? Yes. Not yet approved |  | Laws and policies put in place to enable women to have equal opportunities with men to participate | Policy draft in place and not approved | All employee and councillors stakeholders | Adopt the draft gender policy | Gender responsive council involved in all gender issues in the district | Social Services, Councillors employees | Dec 2017 |  |  |
| Has a gender action plan been drafted and approved? Yes, but not approved. |  |  | An active gender action plan in draft to be approved by the local authority. | Council and all stakeholders | Adoption of the adopted action plan | Gender responsive council plans | Social Services, Gender, Full Council | Dec 2017 |  |  |
| Does the local authority have a Gender champion at political level? Yes, there is a Gender champion at political level |  |  | Local authority has a Gender Champion | Council and stakeholders | Council participates actively in all gender issues in the district and works with other stake holders . | Gender aware council, Gender responsive plans | Council | Dec 2017 |  |  |
| GOVERNANCE |  |  |  |  |  |  |  |  |  |  |
| Representation |  |  |  |  |  |  |  |  |  |  |
| Strategic objective: To ensure that 50% of decision-making positions in all public and private sectors are held by women including through the use of affirmative action measures by 2030. |  |  |  |  |  |  |  |  |  |  |
| What is the % of women councillors in the local authority? 50% 3 women and 3 men | End all forms of discrimination against all women and girls everywhere by 2030 | State Parties shall, ensure equal and effective representation of women in decision making positions in the political, public and private sectors including through the use of special measures as provided for in Article 5. | Percentage of women in local government | Women, girls, boys, men | -Sensitisation of the general public trough workshops -Giving women councillors influential positions of influence and responsibility, e.g chairperson of council is a woman. | 50 % representation of men and women councillors Women councillors being head of committees | Administration | Dec 2017 |  |  |
| What proportion of women councillors are there in leadership positions in the local authority, e.g. as chairs of committees? Chairperson is a woman- Health and housing committee chairperson is woman |  |  | Percentage of women councillors in leadership positions increased no of woman councillors in leadership positions | Women Councillors | Training | Skilled , eloquent and Influential and powerful women councillors. Women councillors involved in decision making | Administration | 2017 |  |  |
| Strategic objective :To educate communities and raise awareness about the importance of women’s equal representation in local authorities |  |  |  |  |  |  |  |  |  |  |
| Has there been a 50/50 campaign or any other awareness raising on women’s equal participation? Yes 50/50 campaigns were conducted with the assistance from Gender links and ministry of women affairs and other stake holders. | Ensure women’s full and effective participation and equal opportunities for leadership at all levels of decision-making in political, economic and public life | Legislative measures and public awareness campaigns to emphasise that women’s representation and participation are an important component of democracy and good governance. | No of awareness campaigns done per quarter Behaviour change among women eg women furthering their studies Percentage of local authority committees headed by women | Men and women, boys and girls | Sensitization and awareness campaigns | Educated community | administration | 2017 |  |  |
| Political participation |  |  |  |  |  |  |  |  |  |  |
| Strategic objective: To increase participation by women because their concerns are often side-lined or overshadowed by political party concerns. |  |  |  |  |  |  |  |  |  |  |
| Is there a platform where women from different political parties come together to discuss their concerns? no | Ensure women’s full and effective participation and equal opportunities for leadership at all levels of decision-making in political, economic and public life | Policies, strategies and programmes for the establishment and strengthening of structures to enhance gender mainstreaming. | policies, strategies and programmes need to be put in place to ensure equal representation of women and men in decision-making | Women and women Councillors | Training of Councillors , attending workshops where they can learn from others | Policy consistence | Administration | 2017 |  |  |
| Has any networking been done with other women’s platforms at other levels e.g district, provincial and national? Yes, Women in Local Government Forum and women in action group, ZWLA and JCT |  |  |  | Women policy makers and employees | Continuous lobbying and provision of the interface for communication through workshops and other means of communication. | Policies that accommodate everyone | administration | 2017 |  |  |
| Strategic objective : To empower women councillors to advocate for gender equality |  |  |  |  |  |  |  |  |  |  |
| Has there been a skills audit? What kinds of skills exist? no. | Enhance the use of enabling technology, in particular information and communications technology, to promote the empowerment of women | Building the capacity of women to participate effectively though leadership and gender sensitivity training and mentoring. | Plan for a skills audit When skills audit is done , recommendations to be implemented | Councillors and staff | Trainings workshops | Staff allocated to jobs according to their skills Salaries allocated according to the skills Proper job descriptions | Administration | 2017 |  |  |
| What training has already been done? Capacity building workshops |  |  | Percentage men and women in gender activities including gender training and community mobilisation activities. |  | Capacity building trainings for men and women. | Capacitated men and women in gender related activities( behaviour change) | Administration | 2017 |  |  |
|  |  |  |  | Men and women staff and councillors | Trainings and workshops | Capacitated men and women | Administration | 2017 |  |  |
|  |  |  | No. of trainings conducted. | Staff and councillors | Trainings and workshops done | Capacitated men and women | Administration | 2017 |  |  |
| Strategic objective : To empower men on gender issues and mobilise their support |  |  |  |  |  |  |  |  |  |  |
| What training has already been done – how many men participated? 60% |  | By 2030, State Parties must ensure the inclusion of men in all gender-related activities, including gender training and community mobilisation. | No. of men trained on gender issues 300 | Men councillors, staff and men government officials. | Capacity building workhops for men and women | Capacited men and women | HRD and Administration | 2017 |  |  |
|  |  |  | No. of trainings conducted 4 | Men councillors, staff and men government officials. | Capacity building workshops for men and women | Capacitated men and women | Administration | 2017 |  |  |
| How many dialogues with male Cllrs have been held? 2 |  |  | Number and types of dialogues held involving men | Male councillors | Holding male councillors dialogues on gender issues. | Sensitized male councillors on gender | Admin | 2017 |  |  |
|  |  |  | No. of male councillors attending dialogues | Male councillors | Holding male councillors dialogues on gender issues. | Sensitized male councillors on gender | Admin | 2017 |  |  |
| Public participation |  |  |  |  |  |  |  |  |  |  |
| Strategic objective : To ensure that women and men participate equally in local government and community matters |  |  |  |  |  |  |  |  |  |  |
| What is the representation of women and men in ward committees? | Ensure women’s full and effective participation and equal opportunities for leadership at all levels of decision-making in political, economic and public life | By 2030 ensure that 50% of decision-making positions in all public and private sectors are held by women including through then use of affirmative action measures. | Percentage of women and men in ward committees | Men and women | To reserve leadership positions for women. Capacity building for women | 50/50 representation of women and men in ward committees | Administration | 2017 |  |  |
|  |  |  | Committees | Men and women in local government |  | 50/50 representation of women and men in ward committees | Administration | 2017 |  |  |
| Are there gender disaggregated statistics on the consultative meetings? Yes |  | Women and men participate equally in all governance structures. | Gender or sex disaggregated data available (attendance registers) | Women and men in the community | Ensuring that women and men participate equally by giving equal opportunity for participation to both men and women during consultative meetings. | Equal participation of men and women | Admin Department |  |  |  |
| Have any meetings or forums been conducted with men’s groups? Workshops has been held for both men and women by council together with SAYWHAT |  | Ensure the inclusion of men in all gender related activities, including gender training and community mobilisation. | Number of meetings with men’s groups | Men in the community | Holding gender training workshops and campaigns with both men and women as participants | Successful campaigns and workshops with both men and women included | Administration |  |  |  |
| PLANNING |  |  |  |  |  |  |  |  |  |  |
| Strategic objective: To ensure that targeted planning and service delivery takes place in the council women are consulted equally in policy-making processes. |  |  |  |  |  |  |  |  |  |  |
| Is the local authority’s strategic plan gender aware? Yes there is gender mainstreaming in strategic plans. |  |  | An alignment of Strategic plan with gender issues |  | Holding committee meetings: Council , sub- committee, stakeholder feedback and Campaigns. review meetings | Consulted women in policy making process. | Council and government departments. | 2017 |  |  |
|  |  |  | Gender Responsive Strategic Plan adopted | Council | Implementation of the adopted strategic plan | Achieved objectives | Council departments policymakers | 2017 |  |  |
| Strategic objective: To ensure that women are consulted about their needs when drawing up Council plans. |  |  |  |  |  |  |  |  |  |  |
| Has the gender desk been involved in the strategic planning process? Have the views of women and men been taken into account in the plan? Yes, the Gender Focal Person was involved in council strategic planning |  | Equal participation of women and men in policy formulation and implementation of economic policies. | Percentage of women and men involved in the strategic planning Minutes Photos |  | consultation meetings | Holding budget consultation meetings and Ward meetings Consulted district women and men. | Council departments Policy makers | October 2016 |  |  |
|  |  |  |  | Council | Ensuring that there is gender mainstreaming/Gender responsive budgeting. | Gender mainstreaming in council | Administration Finance engineering | 2017 |  |  |
| EMPLOYMENT PRACTICES AND ENVIRONMENT |  |  |  |  |  |  |  |  |  |  |
| Strategic objective: To increase the representation of women employed in the local authority by 2030. |  |  |  |  |  |  |  |  |  |  |
| What steps have been taken to prioritise gender equity in performance plans? Staff development programmes are currently in place therefore female employees are earmarked for decision making positions. Managerial responsibilities are being given to female employees i.e The Town Manager for Murewa, Gender Focal Person, Accountant and District AIDS Coordinators are females. | By 2030, achieve full and productive employment and decent work for all women and men, including for young people and persons with disabilities, and equal pay for work of equal value | States Parties shall conduct time use studies, adopt policy measures to recognize and value unpaid care and domestic work through the provision of public services and infrastructure, and promote shared responsibility between men and women to ease the burden of multiple roles played by women. | Percentage of women in elected positions with a bearing on economic decision making. Are the employment policies and practices gender sensitive? | Employees | Introducing staff development programmes by giving them study leave | Educated and knowledgeable staff | Admin Department | By December 2017. |  |  |
| What are the current gender statistics of employees in the local authority? 249 males and 69 females What % men and women occupy management positions – what is the breakdown per department? Management 3 women to 15 men |  | State Parties shall further implement the provisions on the multiple roles of women in accordance with the SADC Protocol on Employment and Labour | Percentage of women and men in relevant management positions . | employees | Upgraded women and men in positions | women Promoted | Adminstration |  |  |  |
| Selection and recruitment |  |  |  |  |  |  |  |  |  |  |
| Strategic objective: To ensure that the recruitment and selection process offers equal opportunity to women. |  |  |  |  |  |  |  |  |  |  |
| What kind of employment equity plan is in existence? The employment policy is in place and there is equal opportunity for both men and women to apply for jobs | Adopt and strengthen sound policies and enforceable legislation for the promotion of gender equality and the empowerment of all women and girls at all levels | State parties shall undertake reforms to give women equal rights, and opportunity to economic resources and control and ownership over productive resources, land and other forms of property, financial services, inheritance, and natural resources in accordance with national laws. | various equity plans the local authority implements | Vulnerable groups and the disabled persons. | *To advertise for jobs and the advert should encourage ladies and the disabled to apply *To recruit women *The panel should be comprised of at least ladies as well so that the gender be balanced | Increased number of woman from in senior jobs | Admin Department |  |  |  |
| What are the targets for ensuring women’s equal representation at all levels? 50/50 by 2017 |  |  | Skills audit implemented Quota of various departments with regards to women’s representation at various levels |  | Introducing staff development programmes by assisting female employees with educational loans, study leaves and giving decision making responsibilities. | Increased no of women positions in upper grades | Admin Department | By December 2017. |  |  |
| Has gender been incorporated into policies and processes? no |  | Eradication of occupational segregation and all forms of employment discrimination. | Craft policies and recruitment policies |  | Incorporate gender into policies crafted | Adopted gender incorporated policies | administration | December 2017 |  |  |
| Are women and men paid equally for the work they do? Yes they are paid equally | By 2030, achieve full and productive employment and decent work for all women and men, including for young people and persons with disabilities, and equal pay for work of equal value | States Parties shall, with regard to the special measuresprovisions in Article 5, develop strategies to ensure that women benefit equally from economic opportunities, including those created through public procurement processes | -grading and remuneration schedule | All employees and policy makers | Implemented proper grading and remuneration schedules | Fairly paid employees when they do the same job | Admin Department | December 2017 |  |  |
| What is the policy on maternity leave and paternity leave? In terms of the Labour Act, three months maternity leave and breastfeeding periods as per the Labour Act as well. No paternity leaves are being granted. | Adopt and strengthen sound policies and enforceable legislation for the promotion of gender equality and the empowerment of all women and girls at all levels. | Enact and enforce legislative measures prohibiting the dismissal or denial of recruitment on the grounds of pregnancy or maternity leave. | Draft or adopted Policy in place for maternity leave and paternity leave |  | Approval of maternity leave. To discuss further on issues regarding paternity leaves. | Educated employees on the labour Act- (maternity, paternity and compassionate leave) | Admin Department | December 2017 |  |  |
| Capacity building |  |  |  |  |  |  |  |  |  |  |
| Strategic objective: To ensure that training is done to educate all employees and community groups on gender |  |  |  |  |  |  |  |  |  |  |
| What training has already been done? Councillors Capacity Building Workshop Training facilitated by Gender Links and ministry of women affairs , ZWLA and JCT |  | State Parties shall review, amend and enact laws and policies that ensure women and men have equal access to wage employment, to achieve full and productive employment, decent work including social protection and equal pay for work of equal value for all women and men. | Number of capacity training given on policies and strategies. |  | Conducting trainings on: *GBV at workplace, Gender awareness campaigns | Educated and gender sensitive employees, board (councillors) and community | Admin department | December 2017 |  |  |
| Work conditions and environment |  |  |  |  |  |  |  |  |  |  |
| Strategic objective: Address issues of sexual harassment in the local authority. |  |  |  |  |  |  |  |  |  |  |
| Is there a sexual harassment policy in existence? There is an adopted sexual harassment policy | Eliminate all forms of violence against all women and girls in the public and private spheres, including trafficking and sexual and other types of exploitation | States Parties shall: by 2030, enact and enforce legislation prohibiting all forms of gender based violence; | Percentage of women and men experiencing sexual harassment in work place | employees | *Adopted Sexual harassment policy by Full Council *Educating the employees on sexual harassment policy | Sexual harassment policy in place. Knowledgeable and motivated employees on sexual harassment. | Admin | December 2017 |  |  |
| What kind of safety measures are in place currently? Penalties/charges in the code of conduct |  | Ensure that perpetrators of gender based violence, including domestic violence, rape, femicide, sexual harassment, female genital mutilation and all other forms of gender based violence are tried by a court of competent jurisdiction |  |  |  | Sexual harassment policy in place. Knowledgeable and motivated employees on sexual harassment. | Admin | December 2017 |  |  |
| LOCAL ECONOMIC DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |
| Strategic objective : To facilitate access to equal employment opportunities |  |  |  |  |  |  |  |  |  |  |
| Is there gender disaggregated data on jobs created through the local authority’s local economic development activities? NO | Undertake reforms to give women equal rights to economic resources, as well as access to ownership and control over land and other forms of property, financial services, inheritance and natural resources, in accordance with national laws | By 2030, review, amend and enact laws and policies that ensure women and men have equal access to wage employment in all sectors of the economy. | Percentage women owning businesses, land and property Percentage of women accessing financial services | women, men, youth ,Elderly & People with Disability | Gender mainstreaming on all, Gender awareness meetings | 50. Reduced unemployment rate and demand for work space | Finance committee, | December 2017 |  |  |
|  | By 2030, ensure that all men and women, in particular the poor and the vulnerable, have equal rights to economic resources, as well as access to basic services, ownership and control over land and other forms of property, inheritance, natural resources, appropriate new technology and financial services, including but not limited to microfinance as a the primary source of access. |  |  | women, men, youth ,Elderly &People with Disability | Facilitation of business management training, Workplace allocation |  | Finance committee, Gender committee | December 2017 | 200 |  |
| Strategic objective : To provide gender aware support to the emerging business sector including micro enterprise |  |  |  |  |  |  |  |  |  |  |
| How gender aware is the local authority’s assistance to the development of local businesses with an emphasis on emerging businesses? Council is gender aware and is considering men and women on allocation of land and other investment opportunities. | By 2030, ensure that all men and women, in particular the poor and the vulnerable, have equal rights to economic resources, as well as access to basic services, ownership and control over land and other forms of property, inheritance, natural resources, appropriate new technology and financial services, including but not limited to microfinance as a the primary source of access. | State parties shall by 2030, adopt policies and enact laws which ensure equal access, benefits and opportunities for women and men in trade and entrepreneurship, taking into account the contribution of women in the formal and informal sectors. | Policies and programmes in place to support entrepreneurship development; especially for women, youth, people with disabilities and emerging entrepreneurs. | women, men, youth ,Elderly & People with Disability | Gender awareness meetings, Gender mainstreaming on all. Local economic development policy. | Gender informed informal sector | Finance committee, | December 2017 |  |  |
| Strategic objective : To ensure that women and men have equal access to appropriate financial resources |  |  |  |  |  |  |  |  |  |  |
| Does the local authority have any financial schemes or influence over any financial schemes to assist LED? Are these gender aware? no | By 20130 ensure that men and women have access to appropriate and inclusive financial services and that these are designed and implemented to address the access to finance barriers faced by women in particular. | Policies and laws that determine access to, control of, and benefit from productive resources by women in order to ensure that women have equal access and rights to credit, capital, mortgages, security and training as men. |  | women, men, youth ,Elderly & People with Disability | Gender mainstreaming in all |  |  |  |  |  |
| Strategic objective:To ensure that women and men have equal access to new technologies for improving the efficiency of their enterprises. |  |  |  |  |  |  |  |  |  |  |
| Does the local authority have any technology schemes or influence over any technology schemes to assist LED? Are these gender aware? NO.. |  | Ensure that women have equal rights to access training and opportunities in technological fields such as IT and engineering. |  |  |  |  |  |  |  |  |
| Procurement |  |  |  |  |  |  |  |  |  |  |
| Strategic objective: To ensure that women benefit equally from the procurement processes which they have historically been excluded from. |  |  |  |  |  |  |  |  |  |  |
| What proportion of the local authority’s tenders over the last year went to women? Is there a policy and or point system in place to redress gaps? | By 2030, empower and promote the social, economic and political inclusion of all, irrespective of age, sex, disability, race, ethnicity, origin, religion or economic or other status Promote public procurement practices that are sustainable, in accordance with national policies and priorities | State Parties shall, by 2030, and with regard to the affirmative action provisions of Article 5, introduce measures to ensure that women benefit equally from economic opportunities, including those created through public procurement processes. | Countries with legislated instruments for women, men, youth ,Elderly & People with Disability ’s equal participation in tenders at a national, provincial and local level and in all sectors of the economy | Women, men ,youth | Encourage business women to register with the State Procurement Board. | Women benefiting equally from economic opportunities. | Procurement committee | December 2017 |  |  |
|  |  | States Parties shall, by 2030, review their national trade and entrepreneurship policies, to make them gender responsive | Number of national and trade policies that prepare prospective entrepreneurs and promote the interests of women in business. | Women, men ,youth | Gender awareness meetings, Gender mainstreaming on all | *Trade policy *Women benefiting equally from economic opportunities. | Finance committee, Gender committee | December 2017 | 500 |  |
|  |  | State parties shall by 2030, undertake reforms to give women equal rights, and opportunity to economic resources and control and ownership over productive resources, land and other forms of property, financial services, inheritance, and natural resources in accordance with national laws. | Number of women, men, youth ,Elderly & People with Disability with access to: - Economic prospects - Control and ownership over land, property and other productive resources. - Access to appropriate and inclusive funding sources for businesses. |  |  |  | Finance committee, Gender committee | December 2017 |  |  |
| CLIMATE CHANGE AND SUSTAINABLE DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |
| Strategic objective: Ensure that the local authority understands the effects of climate change and they address the effects through instilling measures to address the negative impact of climate change by 2030. |  |  |  |  |  |  |  |  |  |  |
| Has there been a gender aware audit done of climate change and its effects and or likely effects? no. | Promote mechanisms for raising capacity for effective climate change-related planning and management in least developed countries and small island developing States, including focusing on women, youth and local and marginalized communities | State Parties shall: - develop policies, strategies, and programmes to address the gender issues in Climate Change in accordance with the SADC Protocol on Environment and Sustainable Development. - conduct research to assess the differential gendered impacts of climate change and put in place effective mitigation and adaptation measures. |  |  |  |  |  | 2017 |  |  |
|  |  | State Parties shall by 2030 should provide access to clean water and renewable energy technologies to all households, particularly to rural women, including by investing in and promoting the development of alternative safe and clean energies (such as hydropower and solar) in order to reduce reliance on non-sustainable energy sources. |  | women, men, youth, elderly, people with disability, child headed families and indigenous, peoples, | -Awareness campaigns -Mobilising communities to use other sources of energy -Trainings on conservation methods | -Established woodlots -Conserved environment - | Environment committee, EMA, Forestry Commission, Ministry of Lands, Gender Committee, Projects and Planning Committee | 2017 |  |  |
| Strategic objective: To involve women, as key stewards of the environment, in environmental preservation |  |  |  |  |  |  |  |  |  |  |
| Are women involved in drawing up policies and plans for “going green” no | Improve education, awareness-raising and human and institutional capacity on climate change mitigation, adaptation, impact reduction and early warning | State Parties shall design gender responsive capacity building, education, and training on environmental management, and climate change for sustainable development initiatives |  |  |  |  |  | 2017 |  |  |
| Are there any green business ventures? Yes Irrigation schemes are being resuscitated for horticulture projects, | By 2030, ensure sustainable food production systems and implement resilient agricultural practices that increase productivity and production, that help maintain ecosystems, that strengthen capacity for adaptation to climate change, extreme weather, drought, flooding and other disasters and that progressively improve land and soil quality. | State Parties shall by 2030 develop and implement gender responsive policies, strategies, projects and programmes for environmental management, disaster reduction especially on climate change for sustainable development. | environmental management, climate change and sustainable development projects are done | women, men, youth, elderly, people with disability, child headed families and indigenous | -Budgeting for environmental management, climate change and sustainable development. | Costed Action plans | admin | 2017 |  |  |
|  |  |  | No. Of gardens owned by women | Women and men | -Mobilising women to embark into green ventures. -Providing space for women to engage into green ventures. |  |  | 2017 |  |  |
| Are there any Programmes and workshops to increase knowledge on improving climate change? Yes |  |  | Awareness programmes and workshops to educate all the designated groups on sustainable greening | Men and women, youths, people living with disabilities | Awareness campaigns, sensitization meetings, | Knowledgeable communities | HRD and Admin, Gender Committee | 2017 |  |  |
| Are there any Programmes targeting young people on sustainable greening? |  |  | Types and number of programmes on sustainable greening | Young boys and girls, schools | Greening projects |  | Environment committee Forestry commission | 2017 |  |  |
| Are there any policies on sustainable development? Environmental by-laws are in place. |  |  | Development of climate change policies | Men, women, business people, people living with disability, youths | Enforcement of environmental by-laws | Environmental by-laws. | Environment committee | 2017 |  |  |
| Strategic objective: To take into account the needs of women in emergencies and disasters. |  |  |  |  |  |  |  |  |  |  |
| How gender aware are existing disaster management plans? The district disaster management takes into consideration both men and women therefore it is gender aware. |  | State Parties shall by 2030 develop and implement gender responsive policies, strategies, projects and programmes for environmental management, disaster reduction especially on climate change for sustainable development | Local authority plans on environmental management, climate change and sustainable development. | Men, women, business people, people living with disability, youths | Crafting and adoption of disaster management plans or policies. | Gender aware disaster management plan. | District Disaster Management committee | 2017 |  |  |
| INFRASTRUCTURE AND SOCIAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |
| Housing |  |  |  |  |  |  |  |  |  |  |
| Strategic objective: To promote the equal rights of women to land tenure |  |  |  |  |  |  |  |  |  |  |
| What proportion of stands is owned by women, men, youth, Elderly & People with Disability? 1: 4 stands are owned by women | By 2030, ensure access for all too adequate, safe and affordable housing and basic services and upgrade slums. | Collect and analyse baseline data against which progress in achieving targets will be monitored. | National laws on inheritance Percentage of women, men, youth ,Elderly & People with Disability owning land and houses | Women, man, youth ,Elderly &People with Disability | Continuously updating gender disaggregated data. | Equal men and women owning properties | Housing department | December 2017 |  |  |
| Strategic objective: To women’s equal access to housing. |  |  |  |  |  |  |  |  |  |  |
| Do any policies exist to ensure women’s access to land tenure? Yes: Land and Housing policy draft | Undertake reforms to give women equal rights to economic resources, as well as access to ownership and control over land and other forms of property, financial services, inheritance and natural resources, in accordance with national laws | State parties shall by 2030, review all policies and laws that determine access to, control of, and benefit from, productive resources by women in order to: End all discrimination against women and girls with regard to water rights and property such as land and tenure thereof; | Implementation of all National laws on ownership of land & houses. | Women | Implementation of land and housing policy. Adoption of the land and housing policy. | Equally distributed land. land and housing policy which addresses gender issues. | Planning and housing department | December 2017 |  |  |
| What kind of consultation process exists in residential design? Holistic consultations of stakeholders through EIA, sensitization meetings with stakeholders. | By 2030, ensure access for all too adequate, safe and affordable housing and basic services and upgrade slums. |  | Number of people who regained their land via land claim programmes | Women | Conducting of consultation and sensitization meetings with stakeholders | Well informed stakeholders | Environment committee | December 2017 |  |  |
|  |  |  | No. of consultative meetings. Percentage of women. Youths and PWDs attending consultative meetings |  |  |  |  |  |  |  |
| Water and sanitation |  |  |  |  |  |  |  |  |  |  |
| Strategic objective: To ensure that women, who are disproportionately affected by inadequate service delivery, are provided with affordable access to basic services |  |  |  |  |  |  |  |  |  |  |
| What services are currently being provided and at what cost? Water and sewer reticulation in high density areas and medium density , borehole repairs in all areas. | By 2030, achieve universal and equitable access to safe and affordable drinking water for all | State parties shall by 2030, review all policies and laws that determine access to, control of, and benefit from, productive resources by women in order to: .End all discrimination against women and girls with regard to water rights and property such as land and tenure thereof. | Number of women, men, youth ,Elderly & People with Disability with access to basic services | women. Youths and PWDs | Budgeting for repairs and maintenance of boreholes, -mobilizing funds for new water and sewer works from community. - | Reticulated residential areas. -clean environment | Roads and works department, Environment department |  |  |  |
|  |  |  | Community Consultative meetings: | Women, men and children | Educating the community on the importance of attending and participating in consultation meetings in wards | Informed community | Roads and Works Department |  |  |  |
| What kind of consultation process has there been in the past? Participatory approach | By 2030, achieve access to adequate and equitable sanitation and hygiene for all and end open defecation, paying special attention to the needs of women and girls and those in vulnerable situations |  |  |  |  |  |  |  |  |  |
| What is the percentage total coverage (urban and/or rural) of sanitation facilities? 78% bothurban and rural |  |  |  |  |  |  |  |  |  |  |
| Social development |  |  |  |  |  |  |  |  |  |  |
| Strategic objective: To make community and sporting facilities more accessible to women and girls and ensure that they benefit equally from such facilities. |  |  |  |  |  |  |  |  |  |  |
| What kind of work is/ has been done with women, men, youth ,Elderly & People with Disability? Agricultural projects SACCOs | By 2030, provide universal access to safe, inclusive and accessible, green and public spaces, in particular for women and children, older persons and persons with disabilities | Collect and analyse baseline data against which progress in achieving targets will be monitored. | Number of awareness programmes and workshops to educate them on sustainable greening and safe public spaces | Women, men ,youth, elderly and people with disability | awareness campaigns and workshops to educate people on sustainable greening and safe public spaces | Educated Women, men ,youth, elderly and people with disability | Environmental health department | December 2017 |  |  |
| SEXUAL REPRODUCTIVE HEALTH, AND HIV AND AIDS AND WELL BEING |  |  |  |  |  |  |  |  |  |  |
| Strategic Objective: Reduce the maternal mortality. |  |  |  |  |  |  |  |  |  |  |
| What is the Maternal mortality ratio? No maternal deaths have been recorded in 2016 |  | Develop and implement policies and programmes to address the mental, sexual and reproductive health needs of women and men in accordance with the Programme of Action of the ICPD and the Beijing Platform for Action. | Maternal mortality ratio | Pregnant mothers | - -Establish more satellite clinics | Reduced maternal mortality | Administration | December 2017 |  |  |
| What is the percentage of births attended by skilled health personnel? 40% |  |  | Percentage of births attended by skilled health personnel | Pregnant mothers and their partners | - -Establish clinics -Awareness campaigns | Reduced number of home deliveries | administration | December 2017 |  |  |
| What is the coverage of iron? -folic acid supplements for pregnant women All the health facilities are offering iron supplements to pregnant mothers who book for ante-natal care |  |  | Coverage of iron -quantity compared to demand and population of folic acid supplements for pregnant women -number of women booked for ante-natal-care. - percentage of women receiving iron-folic acid supplements | Pregnant mothers | -Procurement of iron supplements | Increase in the number of pregnant women receiving iron folic acid supplements | Administration | December 2017 |  |  |
| What is the contraceptive prevalence rate? ---- |  | Develop and implement policies and programmes to address the mental, sexual and reproductive health needs of women and men in accordance with the Programme of Action of the ICPD and the Beijing Platform for Action. | Contraceptive prevalence rate (per number visited the family planning) and distribution. | Sexually active people | -sensitisation meetings on family planning | -increase in the number of people using contraceptives | administration | December 2017 |  |  |
| What is the met demand for family planning? Family planning methods are accessible at all health facilities. Furthermore, condoms are accessible in all the parts of the district and all work places |  |  | Met demand for family planning (percentage of women helped with family planning) | Sexually active people | -sensitisation meetings on family planning -Ensure family planning methods are available in all the wards | -Increase in the number of sexually active people receiving | Administration | December 2017 |  |  |
| What is the Percentage of young people receiving comprehensive sexuality education? 70 % of the young people are receiving comprehensive sexuality education in all health facilities and schools |  |  | Percentage of young people receiving comprehensive sexuality education | Youths | -Sensitisation meetings for youths | Increase in the percent of young people receiving comprehensive sexuality education | Administration department Ministry of women affairs Family support trust. | December 2017 |  |  |
| Strategic objective: Ensure health facilities are accessible to women |  |  |  |  |  |  |  |  |  |  |
| How many mobile clinics are there currently? Which communities do these clinics service? No mobile clinics | Achieve universal health coverage, including financial risk protection, access to quality essential health-care services and access to safe, effective, quality and affordable essential medicines and vaccines for all | State parties shall on issues relating to health, adopt and implement legislative frameworks, policies, programmes and services to enhance gender sensitive, appropriate and affordable quality health care. | Number of mobile clinics available | Women | -Application for mobile clinics to the MOHCC -Budgeting for setting up of mobile clinics | Number of mobile clinics available | NGOs Council | December 2017 |  |  |
| HIV AND AIDS AND CARE WORK |  |  |  |  |  |  |  |  |  |  |
| Prevention |  |  |  |  |  |  |  |  |  |  |
| Strategic objective: To establish the gendered dimensions of HIV/AIDS and to raise awareness on the pandemic in the Local authority. |  |  |  |  |  |  |  |  |  |  |
| Does the local authority have gender disaggregated data on HIV and AIDS? No | By 2030, end the epidemics of AIDS, tuberculosis, malaria and neglected tropical diseases and combat hepatitis, water-borne diseases and other communicable diseases | States Parties shall take every step necessary to adopt and implement gender sensitive policies and programmes, and enact legislation that will address prevention, treatment, care and support in accordance with, but not limited to, the Maseru Declaration on HIV and AIDS; SADC Sponsored CSW resolution on Women, Girls and HIV; UN Political Declaration on HIV and AIDS. | Statistics on HIV and AIDS and other diseases No. of gender aware campaigns No. of female condoms distributed Percentage of females using female condoms |  |  |  |  |  |  |  |
| Do prevention campaigns emphasise differences in power relations between women and men? Yes |  |  |  | Men, women, youth | -Prevention campaigns -Sensitisation meetings | Well informed community | administration | December 2017 |  |  |
| Do prevention campaigns emphasise the dangers of multiple concurrent partners? Yes, |  |  |  | Men, Women, Youth | -Sensitisation meetings | Reduction in the number of people with Multiple concurrent partnerships | Council administration department. | December 2017 |  |  |
| Strategic objective: To run gender- aware prevention campaigns |  |  |  |  |  |  |  |  |  |  |
| Is the female condom available? If so where? They are available in all public toilets and health facilities for free. | By 2030, ensure universal access to sexual and reproductive health-care services, including for family planning, information and education, and the integration of reproductive health into national strategies and programmes. | Adopt and implement legislative frameworks, policies, programmes and services to enhance gender sensitive, appropriate and affordable quality health care. | Provision of female condoms in government buildings, health facilities and NGO’s | Sexually active people | -Condom promotion awareness meetings | Increase in condom distribution and use | Administration Family support trust | December 2017 |  |  |
|  |  |  | number of female condoms(boxes) distributed | Sexually active people | -Distribution of condoms | Increase in condom distribution and use | Administration Family support trust | December 2017 |  |  |
|  |  |  | No. of collection points for female condoms | Sexually active people | -Training of condom depot holders | Increase in condom distribution and use | Administration Family support trust | December 2017 |  |  |
|  |  |  | Percentage of females accessing sexual and reproductive services | Sexually active people | -Awareness meetings | Reduction in STIs, unplanned pregnancies and new infections | Administration Family support trust | December 2017 |  |  |
|  |  |  | No. of clinics/organisations offering sexual and reproductive services | Sexually active people | -Awareness meetings | Reduction in STIs, unplanned pregnancies and new infections | Administration Family support trust | December 2017 |  |  |
| Strategic objective: To ensure that messages of generational sex and multiple partners are addressed |  |  |  |  |  |  |  |  |  |  |
| How has the local authority participated in awareness campaigns in the past? Has the local authority actively participated and promote the 16 Days Campaign in the past? Yes, through attending the commemorations | By 2030, ensure universal access to sexual and reproductive health-care services, including for family planning, information and education, and the integration of reproductive health into national strategies and programmes. | Adopt and implement legislative frameworks, policies, programmes and services to enhance gender sensitive, appropriate and affordable quality health care. | No. of awareness campaigns attended by the Local authority | Men, women, boys and girls | Commemorate 16 Days of activism and providing material assistance | Commemorations done Sensitised communities | Social services NGOs and council | December 2017 |  |  |
| Are there any awareness campaigns in the local authority on the link between gender violence, HIV and AIDS? Yes, |  | Information on services available to survivors of gender based violence AND Laws on gender based violence provide for the comprehensive testing, treatment and care of survivors of sexual offences, which shall include preventing the onset of sexually transmitted infections. | Number of awareness campaigns conducted No. of awareness campaigns on the link between GBV, HIV and AIDS | Men, women youth | -to craft workplace policy -Awareness campaigns | -Increase in the uptake of treatment | Social Services Committee | December 2017 |  |  |
| Strategic objective: To educate women who are not aware of the need to avail themselves of Post Exposure Prophylaxis (PEP) and emergency contraception in the event of a sexual assault. |  |  |  |  |  |  |  |  |  |  |
| Is PEP readily available at all health facilities? If not, at how many facilities is it available? PEP is available at all health facilities | Eliminate all forms of violence against all women and girls in the public and private spheres, including trafficking and sexual and other types of exploitation | States Parties shall, ensure that laws on gender based violence provide for the comprehensive testing, treatment and care of survivors of sexual offences, which shall include: - emergency contraception; - ready access to post exposure prophylaxis at all health facilities to reduce the risk of contracting HIV; and c. preventing the onset of sexually transmitted infections | No. of health facilities offering PEP Percentage of women infected receiving PEP | Sexual Violence survivors | -setting up of more council satellite clinics | Increase in the number of health facilities offering PEP | Administration | December 2017 |  |  |
| Strategic objective: To educate women and men on voluntary counselling and testing which is a powerful tool for preventing the spread of HIV/AIDS. |  |  |  |  |  |  |  |  |  |  |
| What is the % of men and women who go for HTS? 20 % men and 80 % women |  | Collect and analyse baseline data against which progress in achieving targets will be monitored. | Number of women and men counselled for HCT | Women and men | -HTS campaigns -awareness campaigns | Increase in the number of people who know their status. | Administration Social services | December 2017 |  |  |
|  |  |  | Percentage of men and women tested for HIV | Women and men | -HTS campaigns | Increase in the number of people who know their status. | Administration Social services | December 2017 |  |  |
| Treatment |  |  |  |  |  |  |  |  |  |  |
| Strategic objective: To address unequal access to treatment; especially inhibitions by men to accessing treatment |  |  |  |  |  |  |  |  |  |  |
| What proportion of women compared to men access free treatment 5:1 | Ensure universal access to sexual and reproductive health and reproductive rights as agreed in accordance with the Programme of Action of the International Conference on Population and Development and the Beijing Platform for Action and the outcome documents of their review conferences | Ensure universal access to HIV and AIDS treatment for infected women, men, girls and boys by 2030. | Free treatment access ratio Percentage of men and women on ART | Vulnerable groups People living with HIV/AIDS Men women | Ensuring that all patients visiting a health centre receive treatment. Ensuring that drugs are always available at health centres. Sensitizing men and women to go for treatment | Equal access to treatment | Social Service Council administration department | December 2017 |  |  |
| Care |  |  |  |  |  |  |  |  |  |  |
| Strategic objective: Ensure that the local authority addresses the gendered dimensions of care work |  |  |  |  |  |  |  |  |  |  |
| What proportion of care givers in the community are women? 90 % are women | Recognize and value unpaid care and domestic work through the provision of public services, infrastructure and social protection policies and the promotion of shared responsibility within the household and the family as nationally appropriate | State Parties shall, by 2030 develop and implement policies and programmes to ensure the appropriate recognition of the work carried out by caregivers, the majority of whom are women, and to allocate resources and psychological support for caregivers as well as promote the involvement of men in the care and support of people living with HIV and AIDS | Number of women that are care givers. | Percentage of female care givers | Sensitising men on the issue that care work is for both men and women | Recognition of work carried out by caregivers. A sensitised community | Soci | December 2017 |  |  |
| Do care givers receive any remuneration? No. Caregivers give do not receive remuneration |  |  |  |  |  | Motivated caregivers | Social Services NGOs |  |  |  |
| What support do care givers receive? They receive kits, bicycles and uniforms |  |  | No. of care givers receiving support |  | Monitoring and evaluation of caregivers work | Improved skills on care work | Social Services NGOs |  |  |  |
| Do care givers receive training? What kind? Yes they receive basic care training |  |  | Number of trainings conducted for care givers. |  |  | Well Trained caregivers | Social Services NGOs |  |  |  |
|  |  |  | No. of care givers trained |  |  | Well Trained caregivers | Social Services | December 2017 |  |  |
| Are there any efforts to involve men in care work? There is equal opportunity for men and women to volunteer for care work |  |  | -Number of awareness campaigns conducted |  |  |  | Social Services Committee | December 2017 |  |  |
|  |  |  | -Number of dialogues held with men specifically on importance of care work. Percentage of mate care workers | Men | -Dialogues with men | Increase in the number of male care workers | Social Services NGOS | December 2017 |  |  |
| ENDING GENDER BASED VIOLENCE |  |  |  |  |  |  |  |  |  |  |
| Prevention |  |  |  |  |  |  |  |  |  |  |
| Strategic objective: To contribute to the SADC Gender Protocol target of reducing current levels of gender violence by 2030. |  |  |  |  |  |  |  |  |  |  |
| What are the current statistics on GBV in the local authority? Not easy to get statistics from the police | Significantly reduce all forms of violence and related death rates everywhere. | State Parties shall by 2030 adopt integrated approaches, including institutional cross sector structures, with the aim of eliminating current levels of gender based violence. |  |  | -Compilation of local action plan to end GBV | Local action plan to be crafted. | All stakeholders Local authority |  |  |  |
|  |  |  |  | Stakeholders | Have a budget on GBV issues | -GBV activities implemented in the district -decrease in the number of GBV cases reported | Local authority NGOS Ministry of women affairs | December 2017 |  |  |
| Public awareness campaigns |  |  |  |  |  |  |  |  |  |  |
| Strategic objective: To educate communities to challenge and eradicate gender based violence. |  |  |  |  |  |  |  |  |  |  |
| How has the local authority participated in awareness campaigns in the past? Through provision of financial assistance and mobilisation of the community through the councillors and writing letters to the residents and the business community. Has the local authority actively participated and promote the 16 Days Campaign in the past? Yes, through financial assistance and attending the commemoration |  | States Parties shall, review, reform and strengthen their laws and procedures applicable to cases of sexual offences and gender based violence. | Number of campaigns conducted | Men, Women, Youth, Elderly, People living with disabilities, PLHIV | -Awareness campaigns -16 Days of Activism Commemoration | -Decrease in GBV cases | All stakeholders | 2017 |  |  |
| Has the local authority in anyway provided gender awareness education programmes to men and women? Yes, seven 50/50 campaigns |  | Ensure the inclusion of men in all gender related activities including gender training and community mobilisation. | Number of gender awareness programmes run. Number of men that attended. Number or women that attended. | Men and women | -Gender awareness programmes | -Decrease in GBV cases -Increase in the number of men attending gender activities Knowledgeable community | All stakeholders | December 2017 |  |  |
| Response |  |  |  |  |  |  |  |  |  |  |
| Strategic objective: To implement actions that are effective in responding to GBV in your local authority |  |  |  |  |  |  |  |  |  |  |
| To what extent has the local authority promoted the economic development of women to reduce their reliance on others to support themselves? The local authority has given them market stalls where they can sell goods to promote themselves. | Eliminate all forms of violence against all women and girls in the public and private spheres, including trafficking of persons and sexual and other types of exploitation | Put in place harmonised data collection mechanisms to improve researchand reporting on the types and modes of trafficking to ensure effective programming and monitoring. | No of life skills and economic development workshops for survivors of GBV. | -Survivors of GBV | -Life skills and development training workshop | Survivors of GBV who are empowered | All stakeholders | December 2017 |  |  |
| What is the state of street lighting in the local authority? We managed to put 1 tower light and solar street lighting in the CBD |  | By 2030, enact and enforce legislation prohibiting all forms of gender based violence. | Number of areas with electricity | Men and women | -Erect tower lights at all base stations -Erect street lights in all residential areas | Street and tower lights erected | Engineering department | December 2017 |  |  |
|  |  | State Parties shall develop strategies to prevent and eliminate all social, cultural and harmful practices, such as child marriages, forced marriage, teenage pregnancies, and female genital mutilation. |  |  |  |  |  |  |  |  |
| Support |  |  |  |  |  |  |  |  |  |  |
| Strategic objective: To implement a plan and actions that supports survivors of GBV. |  |  |  |  |  |  |  |  |  |  |
| What steps has the local authority taken to economically empower women who have experienced GBV? No steps besides referring them to the NGOS we work with to get help for example Family support trust, child line, social services |  |  |  |  |  |  |  |  |  |  |
| Are any of the police stations within the local authority equipped (private room, female officers etc.) to deal with cases of GBV? They are well equipped and female officers are available |  | State Parties shall, by 2030, review and reform their criminal laws and procedures applicable to cases of sexual offences and gender based violence to eliminate gender bias. | Percentage of referred cases of sexual and gender-based violence against women and children that are investigated and sentenced. | Perpetrators of sexual and gender based violence | -follow ups on reported cases | Perpetrators of sexual and gender based violence investigated and sentenced | Gender committee | December 2017 |  |  |
|  |  | Ensure justice and fairness are accorded to survivors of gender-based violence in a manner that ensures dignity, protection and respect |  | Perpetrators of sexual and gender based violence | -follow ups on reported cases | Perpetrators of sexual and gender based violence investigated and sentenced | VFU Social services | December 2017 |  |  |
| How many places of safety and care are there within the local authority? Not available |  | By 2030, State Parties shall establish special counselling services, legal and police units to provide dedicated and sensitive services to survivors of gender based violence. |  |  |  |  |  |  |  |  |
| How many counselling facilities are there within the local authority? 7 health facilities |  |  | Number of counselling facilities for survivors of gender based violence | GBV survivors | -Offer counselling services frequently | Increase in the number of GBV survivors receiving counselling services | All health facilities | December 2017 |  |  |
| Strategic objective: To ensure information on support to GBV survivors is accessible. |  |  |  |  |  |  |  |  |  |  |
| What publications and information exists on where to get help, and how is this being disseminated currently? No IEC material |  | State Parties shall by 2030; Provide accessible information on services available to survivors of gender based violence. |  | Men and women | - |  | All stakeholders | December 2017 |  |  |
| Coordination |  |  |  |  |  |  |  |  |  |  |
| Strategic objective: To ensure that efforts to address GBV are conducted in a coordinated manner |  |  |  |  |  |  |  |  |  |  |
| Is there a multi sector committee for addressing GBV in the local authority? Yes, we have a gender committee with NGOS and local authority |  | Adopt integrated approaches, including institutional cross sector structures, with the aim of reducing current levels of gender based violence half by 2030. | Number of committee established to address GBV | Stakeholders | -Conduct gender meetings | GBV issues in the district addressed | All stakeholders | December 2017 |  |  |
|  |  |  | Anti-GBV district Task Force in place | Stakeholders |  | GBV issues in the district addressed | All stakeholders | December 2017 |  |  |
|  |  |  |  |  |  | GBV issues in the district addressed | All stakeholders | December 2017 |  |  |
| Budget allocation |  |  |  |  |  |  |  |  |  |  |
| Strategic objective: To ensure that Local authorities commit budgets and resources to addressing GBV |  |  |  |  |  |  |  |  |  |  |
| Is there a budget line for addressing GBV in the Local authority? no |  | Ensure gender sensitive budgets and planning, including designating the necessary resources towards initiatives aimed at empowering women and girls |  |  |  |  |  |  |  |  |
| Monitoring and evaluation |  |  |  |  |  |  |  |  |  |  |
| Strategic objective: To ensure that efforts to address GBV are monitored and evaluated |  |  |  |  |  |  |  |  |  |  |
| What documents on GBV are used by your local authority to inform evidence based programming? -draft gender policy and sexual harassment policy. | By 2020, enhance capacity-building support to developing countries, including for least developed countries and small island developing States, to increase significantly the availability of high-quality, timely and reliable data disaggregated by income, gender, age, race, ethnicity, migratory status, disability, geographic location and other characteristics relevant in national contexts | Collect and analyse baseline data against which progress in achieving targets will be monitored. | No. of capacity building trainings on GBV held. | Stakeholders and council staff | Capacity building training on GBV | Effective implementation of GBV activities | All stakeholders | December 2017 |  |  |
| Best practices |  |  |  |  |  |  |  |  |  |  |
| Strategic objective: To showcase best practices to end GBV |  |  |  |  |  |  |  |  |  |  |
| Has the local authority ever showcased GBV case studies at GL Summits or other platforms?No |  |  | No. of GBV case studies showcased at GL summits |  | Showcase GBV case studies at GL summit | Case studies shared | Gender committee | December 2017 |  |  |
|  |  |  | No. of summit entries mobilised |  | Showcase GBV case studies at GL summit | Case studies shared | Administration department | December 2017 |  |  |
| VISIBILITY AND COMMUNICATIONS |  |  |  |  |  |  |  |  |  |  |
| Strategic objective:To give visibility to the COE process and to the local authority’s commitment to advancing gender equality. |  |  |  |  |  |  |  |  |  |  |
| Is the local authority’s COE status visibly displayed? Yes: Through participating in gender links project activities and community workshops and projects at grass roots level i.e 16 days of activism. |  | State Parties shall by 2030, ensure that women and men can equally access and afford ICTs including internet and hardware | Visibility of COE status | Women, man, youth ,Elderly & People with Disability | To display gender related programme on the website. | COE status visibly displayed? | Admin | December 2017 |  |  |
| Is the local authority’s website linked to the COE page and vice versa? No. |  |  | Website links available. | Women, man, youth ,Elderly & People with Disability | Link council website to the COE page and vice versa? | Website linked to COE. |  | December 2017 |  |  |
| Is the local authority an active member of the Community of Practice? No |  | Build/ strengthen the capacity of media practitioners and the general public to enhance their awareness on gender equality in communication and information, including through social media |  |  |  |  |  |  |  |  |
| No of case studies presented at summits? COE |  |  |  |  |  |  |  |  |  |  |
| GENDER MANAGEMENT SYSTEM |  |  |  |  |  |  |  |  |  |  |
| Gender structures |  |  |  |  |  |  |  |  |  |  |
| Strategic objective: To establish structures that constitute the gender machinery and to ensure that they have the authority to carry out their work and to obtain the commitment of all managers. |  |  |  |  |  |  |  |  |  |  |
| Has any work been done in the establishment of structures? no | Promote peaceful and inclusive societies for sustainable development, provide access to justice for all and build effective, accountable and inclusive institutions at all levels | Establish and strengthen structures to enhance gender mainstreaming. |  |  |  |  |  |  |  |  |
| Is the Gender Management System known, has it been publicised? No |  |  |  |  |  |  |  |  |  |  |
| Is there a committee in the local authority responsible for gender? |  |  |  |  |  |  |  |  |  |  |
| Has gender been written into the performance agreements of senior managers and GFP? No |  |  |  |  |  |  |  |  |  |  |
| Budget, monitoring and evaluation |  |  |  |  |  |  |  |  |  |  |
| Strategic objective: To make use of gender disaggregated data for monitoring and evaluation to ensure that gender equality is being strived for. |  |  |  |  |  |  |  |  |  |  |
| Does sex disaggregated data exist? Is it applied? This is being partly done. |  | Ensure gender sensitive and responsive budgeting at the micro and macro levels, including tracking, monitoring and evaluation. | Tools in place to monitor gender equality Gender specific database on services mandated to the local authority |  | Maintaining sex disaggregated data for monitoring and evaluation to ensure that gender equality is being strived for. | Gender disaggregated data. | Data capturers | 2017 |  |  |
| Strategic objective: To ensure that resources are being allocated to gender priorities. |  |  |  |  |  |  |  |  |  |  |
| Are there direct or budget allocations for advancing gender equality? no |  | Ensure that all national and local budgets sufficiently represent the needs of women and men; assessment of all spending should reflect how resources have been allocated to all gender groups. |  |  |  |  |  |  |  |  |