SEXUAL AND REPRODUCTIVE HEALTH AND RIGHTS (SRHR) CAMPAIGN PLAN-HIV AND AIDS

NAME OF COUNCIL: OSHAKATI

Date:  15 December 2018

Figure 1; Participants seen during HIV AND AIDS Campaign Plan

GUIDANCE ON MESSAGES:

- The group should first decide on and record the specific objectives for the country/council.

- Who are these targeted at?

- What messages/slogans are appropriate to these target groups?

- What are some of the hashtags in country you can leverage on or create? This includes in local languages

- How can they link to regional/global hashtags

- What are some of the Twitter handles you will tag – refer to the Alliance social media handles

| SPECIFIC OBJECTIVES | TARGET GROUPS | MESSAGES/SLOGANS | HASHTAGS – LOCAL | HASHTAGS – REGIONAL/ GLOBAL | Social media tagging |
| --- | --- | --- | --- | --- | --- |
| To promote HIV testing among the youth by 2019 | Youth, adolescents | Stay safe | #Careforyourfuture | #safesex | @UNICEF |
| To promote healthy emotional lifestyle amongst positive youth by 2019 | Youth, adolescents, PLWH | Stay strong | #Be strong | #Keephopealive | @TCE |
| To provide HIV related information and enhance awareness for the youth by 2019 | Youth, Adolescents | Information is important | #healthmattershelps | #beinformed | @UNAIDS |

GUIDANCE ON PLANNING FRAMEWORK:

- Specific objectives should be recorded in the planning framework.

- Actions and activities are suggestions. Please customise as appropriate.  Please be very specific about the activities to be undertaken.

- Delete any suggested activities that are not relevant to your campaign

- Which members of your consortium will be responsible for each activity?

- By When?

- What will be the main outputs?

- What resources will this require, human, financial, other? What synergies can be forged with existing activities? Are there fund raising possibilities?

| OBJECTIVES AND ACTIONS | ACTIVITIES | WHO RESPONSIBLE | TIME FRAME | OUTPUTS | RESOURCES |
| --- | --- | --- | --- | --- | --- |
| Strategic objective | To ensure that the resurgence of HIV and AIDS among young women is curbed in accordance with the SADC protocol on Gender and Development and the SADC sponsored CSW Resolution 50/2 on women, the girl child and HIV. |  |  |  |  |
| Specific objectives: To provide access to sexual reproductive health and rights services by 2019 |  |  |  |  |  |
| 1 | To promote HIV testing among the youth by 2019 |  |  |  |  |
| 2 | To promote healthy emotional lifestyle amongst positive youth by 2019 |  |  |  |  |
| 3 | To provide HIV related information and enhance awareness for the youth by 2019 |  |  |  |  |
| 1. Obtain buy-in from key stakeholders |  |  |  |  |  |
|  | 1.2. Meetings with parliamentarians (who?) | Councillors, CEOs, health directors, school counsellors | March 2019 | Signed Documents | N$1000 |
|  | 1.3 Meetings with statutory bodies – eg law reform commissions – who?) | Councillors, CEO, health directors, school counsellors | April 2019 | Signed Documents | N$3000 |
| 2. Launch the campaign and gain maximum publicity for it | 2.1 Arrange venue, logistics and date for launch | Genderlinks, Councillors, CEO, health directors, school counsellors, Health Ministry, NGOs | June 2019 | Detailed Budget and programme | N$6000 |
| 3. Develop and disseminate campaign materials | 3.1 Pamphlets explaining XXX/ where to get help; disseminated through XXXX | Councillors, CEO, health directors, school counsellors, Health Ministry, NGOs Oshakati town council Ongwediva town council Junior Councillors | July 2019 | Posters and pamphlets | N$1300 |
|  | 3.2 Placing billboards in all strategic areas | Town Councils, Ministry of information, Oshakati town council Ongwediva town council Ministry of health | August 2019 | Placed billboards | N$7000 |
|  | 3.3 Radio: Docu/ drama disseminated via radio and taxis through the taxi association. Use of radio listening clubs to ensure maximum dissemination. | Oshakati town council Ongwediva town council Ministry of information, Ministry of health | September 2019 | Documentations | N$5000 |
| 4. Engage key stakeholders and the general public in interactive public education encounters | 4.1 Workshops in regions/ systematically- ensure all regions covered | Genderlinks, Oshakati town council Ongwediva town council | October 2019 | Workshop reports | N$10000 |
|  | 4.2 Drama using local actors, followed by discussion, that is systematically performed in all districts | Genderlinks, Town Councils Youths , School going Children | October 2019 | Activity report | N$4000 |
| 5. Leverage on special dates in the calendar for promoting the campaign | Sixteen days of activism | Genderlinks, Town Councils Youths , School going Children | December 2019 | Event Report | N$20000 |
|  | 10 December- International Human rights day | Oshakati town council, Ongwediva town council , health directors, school counsellors, Health Ministry, NGOs Junior Councillors,GFPs | December 2019 | Event report | N$6000 |
|  | 1 March- Zero Discrimination Day | Health directors, school counsellors, Health Ministry, NGOs Oshakati town council Ongwediva town council GFPs | March 2019 | Detailed report | N$5000 |
|  | 8 March International Women’s Day | health directors, school counsellors, Health Ministry, NGOs Oshakati town council Ongwediva town council GFPs | March 2019 | Event Report | N$5000 |
|  | 7 April- World Health Day | Oshakati town council Ongwediva town council Health directors, school counsellors, Health Ministry, NGOs | April 2019 | Event Report | N$5000 |
|  | 25 May- Africa Day | Oshakati town council Ongwediva town council school counsellors, Health Ministry, NGOs Junior Councillors, GFPs | May 2019 | Detailed Report | N$4000 |
|  | 11 October-International Day of the Girl Child | Oshakati town council Ongwediva town council Health directors, school counsellors, Health Ministry, NGOs | October 2019 | Detailed Report | N$8000 |
|  | 15 October - International Day of Rural Women | Oshakati town council Ongwediva town council Health directors, school counsellors, Health Ministry, NGOs | October 2019 | Detailed Report | N$2100 |
|  | 21 October-Africa Human Rights Day | Oshakati town council Ongwediva town council health directors, school counsellors, Health Ministry, NGOS | October 2019 | Detailed Report | N$2000 |
|  | 1 November- Africa Youth Day | Oshakati town council Ongwediva town council Health directors, school counsellors, Health Ministry, NGOs | November 2019 | Detailed Report | N$4000 |
| 6. Engage with the mainstream media in obtaining space/ air time for the campaign as well as increasing media coverage | 6.1 Meetings with editors | Oshakati town council Ongwediva town council Health Ministry, NGOs | November 2019 | Minutes | N$500 |
|  | 6.2 Research on coverage of menstrual health in the media | Genderlinks, Universities , polytechnics | December 2019 | Research report | N$8000 |
|  | 6.3 Training for journalists in coverage of menstrual health | CEOs, Gender Links , GFPs, Stakeholders | December 2019 | Training report | N$6000 |
|  | 6.4 Letters/ opinion/ radio talk shows | Oshakati town council Ongwediva town council health directors, school counsellors, Health Ministry, NGOs | December 2019 | Visit report, copies | N$800 |
| 7. To launch a social media campaign | 7.1 Twitter | IT Technician, Genderlinks, | December 2019 | Posted articiles |  |
|  | 7.2 Facebook | IT Technician, Genderlinks, | December 2019 | Posted articiles |  |
|  | 7.3 Instagram | IT Technician, Genderlinks, | December 2019 | Shared articles |  |
|  | 7.4 Website | IT Technician, Genderlinks, | December 2019 | Shared articles |  |
|  | 7.5 GL Community of practise | IT Technician, Genderlinks, Oshakati town council Ongwediva town council Gender committees | December 2019 | Printed articles | N$3000 |
|  | OTHER |  |  |  |  |
| 8. Initiate greater involvement of men in the struggle for women’s human rights | 8.1 Engaging with male champions | Oshakati town council Ongwediva town council health directors, school counsellors, Health Ministry, NGOs | December 2019 | Report | N$9000 |
|  | 8.2 Engaging with men for change networks | Oshakati town council Ongwediva town council health directors, school counsellors, Health Ministry, NGOs | December 2019 | Report | N$4000 |
|  | 9.1 Reports on all workshops and dissemination exercises | Oshakati town council Ongwediva town council Health Ministry, NGOs Genderlinks | Ongoing | Detailed Report | N$9000 |
|  | 9.2 Feedback from the public | Oshakati town council Ongwediva town council Health Ministry, NGOs | Ongoing | Documented Minutes | N$6000 |
| 10. Prepare best practices for the 2019 SADC Protocol@Work #VoiceandChoice Summit | 10.1 Access summit call | GL, Oshakati town council Ongwediva town council | February 2020 | Response to the summit | N$3000 |
|  | 10.2 Document case study | Genderlinks, Champions, GFP | April 2020 | Documented case study | N$3000 |
|  | 10.3 Present case study at the summit | Genderlinks, Champions, GFP | May 2020 | Case study presented | N$5000 |

MONITORING AND EVALUATION

English: http://genderlinks.org.za/what-we-do/sadc-gender-protocol/advocacy/alliance-srhr-me/

French: http://genderlinks.org.za/what-we-do/sadc-gender-protocol/advocacy/alliance-srhr-me/alliance-srhr-se/

Portuguese: http://genderlinks.org.za/what-we-do/sadc-gender-protocol/advocacy/alliance-srhr-me/alianca-srhr-me/