SEXUAL REPRODUCTIVE HEALTH AND RIGHTS (SRHR) CAMPAIGN PLAN – MENSTRUAL HEALTH

NAME OF COUNCIL: EENAHNA

Date: 23 November 2018

Participants are seen during the Menstrual health campaign Plan

GUIDANCE ON MESSAGES:

- The group should first decide on and record the specific objectives for the country/council.

- Who are these targeted at?

- What messages/slogans are appropriate to these target groups?

- What are some of the hashtags in country you can leverage on or create? This includes in local languages

- How can they link to regional/global hashtags

- What are some of the Twitter handles you will tag – refer to the Alliance social media handles

| SPECIFIC OBJECTIVES | TARGET GROUPS | MESSAGES/SLOGANS | HASHTAGS – LOCAL | HASHTAGS – REGIONAL/ GLOBAL | Social media tagging |
| --- | --- | --- | --- | --- | --- |
| EDUCATION - To provide menstrual health education to school girls and women by Dec 2019 | School girls, Women, Female prisoners, Destitute children | Every woman to stay free by ensuring access to Hygienic products | #getituseit | #stayfree | @Freestyle Oshikuku |
| ACCESSIBILITY - To distribute and provide free sanitary pads to women and young girls by Dec 2019 | School girls, Women, Female prisoners, Destitute children | Health ministry provides free pads to women and girls | #accesscounts | #freeaccess | @Unicef |
| DISPOSAL & HYGIENE - To provide efficient disposal and hygienic facilities for sanitary wear | School girls, Women, Female prisoners, Destitute children | -Effective way of disposal and proper provision of proper facilities | #hygieneismy habit | #Menstruationserves | @AmplifyFund |
| SUSTAINABILTY - To develop a sustainable provision of sanitary wear | School girls, Women, Female prisoners, Destitute children | Improve the continuously usage of sanitary wear | #Longlive | #stopthemenstrualtion | #UNAIDS |

| OBJECTIVES AND ACTIONS | ACTIVITIES | WHO RESPONSIBLE | TIME FRAME | OUTPUTS | RESOURCES |
| --- | --- | --- | --- | --- | --- |
| Strategic objective | To ensure that women and girls have access to affordable sanitary ware, including free access in schools, in line with SDG 5 and the SADC Protocol on Gender and Development that commit to universal access to sexual and reproductive health and reproductive rights in accordance with the Programme of Action of the ICPD. |  |  |  |  |
| Specific objectives: What are the specific objectives in your country? For example, has sanitary ware been zero VAT rated? If not, is this an objective? If so what is the next step? Do women and girls have access to sanitary ware? Is sanitary ware freely available in schools? If not, what is the next step? |  |  |  |  |  |
| 1 | To provide menstrual health education to school girls and women by Dec 2019 |  |  |  |  |
| 2 | To distribute and provide free sanitary pads to women and young girls by Dec 2019 |  |  |  |  |
| 3 | To provide efficient disposal and hygienic facilities for sanitary wear by Dec 2019 |  |  |  |  |
| 4 | To develop a sustainable provision of sanitary wear |  |  |  |  |
| 1. Obtain buy-in from key stakeholders | 1.1 Meeting with key officials (who?) | Key Stakeholders NGOs Gender Links Ministry of Gender Churches Ministry of health Schools | Jan 2019 | Drafted Workplan | Venue food Refreshments Stationery |
|  | 1.2. Meetings with parliamentarians (who?) | Key Stakeholders NGOs Gender Links Ministry of Gender Churches Ministry of health Schools | Feb 2019 | Documented minutes | Venue Food Refreshments Stationery |
|  | 1.3 Meetings with statutory bodies – eg law reform commissions – who?) | Key Stakeholders NGOs Gender Links Ministry of Gender Churches Ministry of health Schools | April 2019 | Formulated Policies | Venue Food Refreshments Stationery |
|  | 1.4 Meeting with social actors – eg religious groups – who? | Councils, church leaders, traditional leaders, Special Schools | May 2019 | Information disseminated | Venue Food Refreshments Stationery |
| 2. Launch the campaign and gain maximum publicity for it | 2.1 Agree date and venue for launch, ensuring synergy with other campaigns | Key Stakeholders NGOs Gender Links Ministry of Gender Churches Ministry of health Schools | May 2019 | Minutes indicates Date and venue for launch agreed | Venue Refreshments Stationery |
|  | 2.2 Logistics and planning for the launch | Steering committee | June 2019 | Shared Tasks | Venue Refreshments Stationery |
| 3. Develop and disseminate campaign materials | 3.1 Pamphlets explaining Menstrual health/ where to get help; disseminated through XXXX | Key Stakeholders, NGOs, Gender Links, Ministry of Gender, Ministry of education, Schools | June 2019 | Pamphlets designed and distributed | Stationery Transport |
|  | 3.2 Posters disseminated through Social media networks and put up in strategic places, eg police stations; courts; all gvt. offices; hospitals | public relations officers, GL, Alliance Partners | June 2019 | Posters placed | Transport Refreshments |
|  | 3.3 Billboards are erected at strategic positions | public relations officers, GL, Alliance Partners | June 2019 | Billboards erected | Venue Refreshments Stationery |
| 4. Engage key stakeholders and the general public in interactive public education encounters | 4.2 Drama using local actors, followed by discussion, that is systematically performed in all districts | Health Promotion Officers, Drama Artists | June 2019 | Health promoted District reports | Venue Refreshments |
|  | 4.3 Workshops with specific target groups Traditional leaders Local councillors Schools debates Medical and social worker | Council Steering Committee Logistics departments | June 2019 | Launch programme produced | Venue Stationary transport refreshments |
| 5. Leverage on special dates in the calendar for promoting the campaign | 19 November- World Toilet Day | Ministry of health Town Councils | November 2019 | Toilet paper and Sanitary pads distributed | Transport IEC Food Sanitary ware |
|  | Sixteen days of activism |  |  |  |  |
|  | 8 March International Women’s Day | Council Steering Committee, Logistics departments, Ministry of health |  | Sanitary pads distributed Information disseminated | Transport IEC Food Sanitary ware |
|  | 12 March -Youth Day | Genderlinks Key Stakeholders Ministry of health Ministry of youth Ministry of gender | March 2019 | Sanitary pads distributed Information disseminated | Transport IEC Food Sanitary ware |
|  | 22 March- World Water Day |  |  |  |  |
|  | 7 April- World Health Day | Genderlinks Key Stakeholders Ministry of health Ministry of youth Ministry of gender | April 2019 | Sanitary pads distributed Information disseminated | Transport IEC Food Sanitary ware |
|  | 11 October-International Day of the Girl Child | Genderlinks Key Stakeholders Ministry of health Ministry of youth Ministry of gender | 11 October 2019 | Sanitary pads distributed Information disseminated | Transport IEC Food Sanitary ware |
|  | 15 October - International Day of Rural Women | Ministry of health GL, NGOs Ministry of gender Department of health | 15 October 2019 | Sanitary pads distributed Information disseminated | Transport IEC Food Sanitary ware |
|  | 21 October-Africa Human Rights Day |  |  |  |  |
|  | 1 November- Africa Youth Day | Ministry of health GL, NGOs Ministry of gender Department of health | November 2019 | Sanitary pads distributed Information disseminated | Transport IEC Food Sanitary ware |
|  | World Menstrual Hygiene Day | Ministry of health GL, NGOs Ministry of gender Department of health | May 2019 | Sanitary ware distributed Information disseminated | Sanitary ware IEC material |
| 6. Engage with the mainstream media in obtaining space/ air time for the campaign as well as increasing media coverage | 6.1 Meetings with editors / Breakfast briefings | Media Experts | July 2019 | venue obtained | Transport Venue |
|  | 6.2 Research on coverage of menstrual health in the media | Researchers | July 2019 | Detailed Reports | Research material Transport Stationary |
|  | 6.3 Training for journalists in coverage of menstrual health | IT Experts | March 2019 | Information on menstrual health researched | Research material Transport Stationary |
|  | 6.4 Letters/ opinion/ radio talk shows |  |  |  |  |
| 7. To launch a social media campaign | 7.1 Twitter | IT Technicians | April 2019 | Information disseminated | Laptops |
|  | 7.2 Facebook | IT Technicians | April 2019 | Information disseminated | Laptops |
|  | 7.3 Instagram | IT Technicians | April 2019 | Information disseminated | IT equipment |
|  | 7.4 Website | IT Technicians | April 2019 | Information disseminated | IT equipment |
|  | 7.5 GL Community of practise | IT Technicians | April 2019 | Information disseminated | IT equipment |
|  | OTHER |  |  |  |  |
| 8. Initiate greater involvement of men in the struggle for women’s human rights | 8.1 Engaging with male champions | Genderlinks Key Stakeholders Ministry of health Ministry of youth Ministry of gender | July 2019 | Male champions engaged | Refreshment Transport |
|  | 8.2 Engaging with men for change networks | Genderlinks Key Stakeholders Ministry of health Ministry of youth Ministry of gender | July 2019 | Engaged GFPs | Refreshment Transport |
| 9. Monitor and evaluate the campaign | 9.2 Reports on all workshops and dissemination exercises | Genderlinks Key Stakeholders Ministry of health Ministry of youth Ministry of gender | July 2019 | Materials arranged | Food Refreshment Transport |
|  | 9.3 Media monitoring | Genderlinks Key Stakeholders Ministry of health Ministry of youth Ministry of gender | August 2019 | M&E Officer engaged | tRANSPORT |
|  | 9.4 Speeches | Genderlinks Key Stakeholders Ministry of health Ministry of youth Ministry of gender | August 2019 | Director of proceeding appointed | Refreshment Transport |
|  | 9.5 Feedback from the public | Genderlinks Key Stakeholders Ministry of health Ministry of youth Ministry of gender | August 2019 | Documented minutes | Refreshment Food |
| 10. Prepare best practices for the 2019 SADC Protocol@Work #VoiceandChoice Summit | 10.1 Access summit call | Genderlinks Key Stakeholders Ministry of health Ministry of youth Ministry of gender | September 2019 | Internet accessed | Transport |
|  | 10.2 Document case study | Genderlinks Key Stakeholders Ministry of health Ministry of youth Ministry of gender | November 2019 | GFPs selected | Computer Materials |
|  | 10.3 Present case study at the summit | Gender links, Key Stakeholders, Councils | February 2020 | Presenter arranged | Transport Refreshment Accommodation Meals |

MONITORING AND EVALUATION

English: http://genderlinks.org.za/what-we-do/sadc-gender-protocol/advocacy/alliance-srhr-me/

French: http://genderlinks.org.za/what-we-do/sadc-gender-protocol/advocacy/alliance-srhr-me/alliance-srhr-se/

Portuguese: http://genderlinks.org.za/what-we-do/sadc-gender-protocol/advocacy/alliance-srhr-me/alianca-srhr-me/