SEXUAL AND REPRODUCTIVE HEALTH AND RIGHTS (SRHR) CAMPAIGN PLAN – MATERNAL HEALTH

NAME OF COUNCIL: ONGWEDIVA

Date:  15 December 2018

Figure 1; Participants seen during Maternal health Campaign Plan

GUIDANCE ON MESSAGES:

- The group should first decide on and record the specific objectives for the country/council.

- Who are these targeted at?

- What messages/slogans are appropriate to these target groups?

- What are some of the hashtags in country you can leverage on or create? This includes in local languages

- How can they link to regional/global hashtags

- What are some of the Twitter handles you will tag – refer to the Alliance social media handles

| SPECIFIC OBJECTIVES | TARGET GROUPS | MESSAGES/SLOGANS | HASHTAGS – LOCAL | HASHTAGS – REGIONAL/ GLOBAL | Social media tagging |
| --- | --- | --- | --- | --- | --- |
| To reduce teenage pregnancy by end 2019 | Youth, adolescents School Counselors | Stop early love affairs | #Endyoungsex | #UNICEFGirlsbulletin | @UNICEF |
| To educate the youth on how to maintain healthy relationship and avoid multiple partners | Youth, Young adults | Protect your health | #breakthechain | #UNAIDShealthbulletin | @UNAIDS |
| To provide free SRHR services by 2019 | Community at large | Health for all | #myhealthmyrights | #SADChealthnews | @SAFAIDS |

GUIDANCE ON PLANNING FRAMEWORK:

- Specific objectives should be recorded in the planning framework.

- Actions and activities are suggestions. Please customise as appropriate.  Please be very specific about the activities to be undertaken.

- Delete any suggested activities that are not relevant to your campaign

- Which members of your consortium will be responsible for each activity?

- By When?

- What will be the main outputs?

- What resources will this require, human, financial, other? What synergies can be forged with existing activities? Are there fund-raising possibilities?

| OBJECTIVES AND ACTIONS | ACTIVITIES | WHO RESPONSIBLE | TIME FRAME | OUTPUTS | RESOURCES |
| --- | --- | --- | --- | --- | --- |
| Strategic objective | To ensure that all harmful traditional practices such as genital mutilation are abolished as per Maputo Protocol and the SADC Protocol on Gender and Development. |  |  |  |  |
| Specific objectives: 1 To reduce teenage pregnancy by end 2019 |  |  |  |  |  |
| 2 | To educate the youth on how to maintain healthy relationship and avoid multiple partners |  |  |  |  |
| 3 | To provide free SRHR services by 2019 |  |  |  |  |
| 1. To reduce teenage pregnancy by end 2019 | 1.1 conducting training workshops and awareness on teenage pregnancy by targeting Schools and Churches | NGOs Gender Links Ministry of Gender Ministry of Education Churches Schools | By April 2019 | Letter of Approval from the Ministry of Education | Funds |
|  |  | Oshakati town council Ongwediva Town council |  |  |  |
| 2. To educate the youth on how to maintain healthy relationship and avoid multiple partners | 2.1 Providing life kills trainings to the Youth and young adults | NGOs Gender Links Ministry of Gender Ministry of Justice Churches Schools | By Mid December 2019 | Printed Training Manuals and other materials | Funds |
| 3. To provide free SRHR services by 2019 | 3.1 Engage the Ministry of health for quality service delivery and train health workers | Ministry of health NGOs Gender Links Oshakati town council Ongwediva Town council | By November 2019 | Skilled health Workers | Funds |
| 4. Engage key stakeholders and the general public in interactive public education encounters | 8 March International Women’s Day | Gender Links NGOs Ministry of Gender | March 2019 | Event report | Funds |
|  | 7 April- World Health Day | NGOs Gender Links Ministry of education Ministry of Gender Ministry of health | April 2019 | Event report | Funds |
|  | 29 April-National Youth day | Gender Links Ministry of education Ministry of Gender Ministry of Youth | April 2019 | Event report | Funds |
| 5. Leverage on special dates in the calendar for promoting the campaign | 25 May- Africa Day | Gender Links Ministry of education NGOs | May 2019 | Event report | funds |
|  | 16 June Day- Day of the African Child | Gender Links NGOs Ministry of education Ministry of Gender Ministry of Youth Oshakati town council Ongwediva Town council | June 2019 | Event report | Funds |
|  | 31 July- Pan-African Women’s Day | Gender Links Ministry of education Ministry of Gender Ministry of Youth Oshakati town council Ongwediva Town council | July 2019 | Day commemorated | Funds |
|  | 11 October-International Day of the Girl Child | Gender Links NGOs Ministry of education Ministry of Gender Ministry of Youth Oshakati town council Ongwediva Town council | October 2019 | Event report | Funds |
|  | 15 October - International Day of Rural Women | Gender Links Ministry of education Ministry of Gender Ministry of Youth Oshakati town council Ongwediva Town council | October 2019 | Event Report | Funds |
|  | 25 October-Africa Human Rights Day | Gender Links Key stakeholders Ministry of education Ministry of Gender Ministry of Youth Oshakati town council Ongwediva Town council | October 2019 | Event Report | Funds |

MONITORING AND EVALUATION

English: http://genderlinks.org.za/what-we-do/sadc-gender-protocol/advocacy/alliance-srhr-me/

French: http://genderlinks.org.za/what-we-do/sadc-gender-protocol/advocacy/alliance-srhr-me/alliance-srhr-se/

Portuguese: http://genderlinks.org.za/what-we-do/sadc-gender-protocol/advocacy/alliance-srhr-me/alianca-srhr-me/