SEXUAL AND REPRODUCTIVE HEALTH AND RIGHTS (SRHR) CAMPAIGN PLAN – MATERNAL HEALTH

NAME OF COUNCIL: OUTAPI

Date:  12 December 2018

Figure 1; Participants seen during Maternal health Campaign Plan

GUIDANCE ON MESSAGES:

- The group should first decide on and record the specific objectives for the country/council.

- Who are these targeted at?

- What messages/slogans are appropriate to these target groups?

- What are some of the hashtags in country you can leverage on or create? This includes in local languages

- How can they link to regional/global hashtags

- What are some of the Twitter handles you will tag – refer to the Alliance social media handles

| SPECIFIC OBJECTIVES | TARGET GROUPS | MESSAGES/SLOGANS | HASHTAGS – LOCAL | HASHTAGS – REGIONAL/ GLOBAL | Social media tagging |
| --- | --- | --- | --- | --- | --- |
| To eliminate neonatal morbidity and mortality by 2019 | Young Girls Young adults, Government houses | Zero to mortality rate | #Dienotnow | #VoiceandChoice | @Genderlinks |
| To enhance and promote reproductive health | Adolescents, Ministry of Health | Information is our health | #informationispower | #Healthandpeople | @ACTIONAID |
| To increase contraceptive prevalence and provision of family planning services | Life school teachers, health Ministry, private clinics | One round one condom | #Dieorlive | # Onevoiceoneaction | @ UNAIDS |

GUIDANCE ON PLANNING FRAMEWORK:

- Specific objectives should be recorded in the planning framework.

- Actions and activities are suggestions. Please customise as appropriate.  Please be very specific about the activities to be undertaken.

- Delete any suggested activities that are not relevant to your campaign

- Which members of your consortium will be responsible for each activity?

- By When?

- What will be the main outputs?

- What resources will this require, human, financial, other? What synergies can be forged with existing activities? Are there fund-raising possibilities?

| OBJECTIVES AND ACTIONS | ACTIVITIES | WHO RESPONSIBLE | TIME FRAME | OUTPUTS | RESOURCES |
| --- | --- | --- | --- | --- | --- |
| Strategic objective | To eliminate maternal mortality in line with the SADC Protocol on Gender and Development and SDG 5 that commit to universal access to sexual and reproductive health and Reproductive rights in accordance with the Programme of Action of ICPD. |  |  |  |  |
| Specific objectives: 1 To eliminate neonatal morbidity and mortality by 2019 |  |  |  |  |  |
| 2 | To enhance and promote reproductive health by 2019 |  |  |  |  |
| 3 | To increase contraceptive prevalence and provision of family planning services |  |  |  |  |
| - Obtain buy-in from key stakeholders | 1.1 conducting meetings with the relevant Ministries and key officials | Key Stakeholders NGOs Gender Links Ministry of youth Ministry of health Churches Schools | By April 2019 | Documented minutes | Funds |
|  |  | Town council |  |  |  |
| 2. launch the campaign and gain maximum publicity for it | 2.1 Agree date and venue including logistics and planning for the launch | Key Stakeholders NGOs Gender Links Ministry of youth Ministry of health Churches Schools Town council | By Mid December 2019 | Reports | Funds |
| 3. To empower community with knowledge and skills and create accessibility to maternal services and products | 3.1 Engage the Ministry of health 3.2 Engage relevant stakeholders 3.3 Engage suppliers on quality assurance | Key Stakeholders NGOs Gender Links Ministry of youth Ministry of health Churches Schools Town council | By November 2019 | Reports and documentation | Funds |
| 4. Engage key stakeholders and the general public in interactive public education encounters | 8 March International Women’s Day | Key Stakeholders NGOs Gender Links Ministry of youth Ministry of health Ministry of Gender Churches Schools Town council | March 2019 | Event Reports | Funds |
|  | 7 April- World Health Day | Key Stakeholders NGOs Gender Links Ministry of youth Ministry of health Ministry of Gender Churches Schools Town council | April 2019 | Event Reports | Funds |
|  | 29 April-National Youth day | Gender Links Ministry of education Ministry of Gender Ministry of Youth Town council | April 2019 | Event reports | Funds |
| 5. Leverage on special dates in the calendar for promoting the campaign | 25 May- Africa Day | Key Stakeholders NGOs Gender Links Ministry of youth Ministry of health Ministry of Gender Churches Schools Town council | May 2019 | Event reports | Funds |
|  | 16 June Day- Day of the African Child | Gender Links Key stakeholders NGOs Ministry of education Ministry of Gender Ministry of Youth Town council | June 2019 | Event reports | Funds |
|  | 31 July- Pan-African Women’s Day | Gender Links Ministry of education Ministry of Gender Ministry of Youth Key stakeholders Town council | July 2019 | Event reports | Funds |
|  | 11 October-International Day of the Girl Child | Gender Links Key stakeholders Ministry of education Ministry of Gender Ministry of Youth | October 2019 | Event reports | Funds |
|  | 15 October - International Day of Rural Women | Gender Links NGOs Ministry of education Ministry of Gender Ministry of Youth | October 2019 | Event reports | Funds |
|  | 25 October-Africa Human Rights Day | Key Stakeholders NGOs Gender Links Ministry of youth Ministry of health Ministry of Gender Churches Schools Town council | October 2019 | Event reports | Funds |

MONITORING AND EVALUATION

English: http://genderlinks.org.za/what-we-do/sadc-gender-protocol/advocacy/alliance-srhr-me/

French: http://genderlinks.org.za/what-we-do/sadc-gender-protocol/advocacy/alliance-srhr-me/alliance-srhr-se/

Portuguese: http://genderlinks.org.za/what-we-do/sadc-gender-protocol/advocacy/alliance-srhr-me/alianca-srhr-me/